## BOQ
URC CONSTRUCTION (P) LTD
CLIENT : ODISHA BRIDGE & CONSTRUCTION CORPORATION LIMITED
PROJECT NAME : Design & Construction of Maa Samaleswari Temple Area Under Samalei Plan on Lumpsum Turnkey Basis
Agreement Value (INR) = |  |  |  | 1142000000
ABSTRACT OF WORKS
Contract No: 14/Turnkey-Lump Sum / 22-23
Sl.no | Description of Item In Stage wise | Area | Unit | Weightage in % to the Contract | Sub-Percentage weightage | Amount In the Contract | Sub-Total weightage in Percentage to the Contract Price | Amount In Item wise | % Completed Till Date | Amount Received Till Date
1 | DESIGN STAGE |  |  | 2% |  | 22840000
1.1 | On approval of Inception Report, detail survey and draft architectural drawing & QMP |  |  |  | 25% |  |  | 5710000
1.1.1 | On approval of Inception Report |  |  |  | 30% |  | 1713000
1.1.2 | Detail survey Report |  |  |  | 30% |  | 1713000
1.1.3 | Draft of Architectural Drawing |  |  |  | 30% |  | 1713000
1.1.4 | Supmisson of QMP |  |  |  | 10% |  | 571000
1.2 | On approval of Site development plan and architectural drawing |  |  |  | 25% |  |  | 5710000
1.2.1 | Site development plan |  |  |  | 50% |  | 2855000
1.2.2 | Final architectural drawings |  |  |  | 50% |  | 2855000
1.3 | On approval of MEP |  |  |  | 25% |  |  | 5710000
1.3.1 | On approval of Design basis report showing electrical, sanitary, Fire Fighting |  |  |  | 30% |  | 1713000
1.3.2 | On approval of Electrical drawings |  |  |  | 30% |  | 1713000
1.3.3 | On Approval of PHE drawings |  |  |  | 20% |  | 1142000
1.3.4 | On approval of Firefighting drawings |  |  |  | 20% |  | 1142000
1.4 | On approval of final Architectural drawing showing electrical and sanitary layout plan and detail structural design and interior design/decoration |  |  |  | 25% |  |  | 5710000
1.4.1 | On approval of final Architectural drawing showing electrical and sanitary layout plan |  |  |  | 60% |  | 3426000
1.4.2 | On approval of final structural design and interior design/decoration |  |  |  | 40% |  | 2284000
2 | CONSTRUCTION STAGE
2.1 | Religious Facilities, Pilgrim Facilities, Information Counter, Vending Zone, Shoe Store, Crematorium, Clock Tower.
A | On Completion up to Plinth |  |  | 3% |  | 34260000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 2792376.5566
1.1 | Excavation |  |  |  | 5% |  | 139618.8278
1.2 | ATT |  |  |  | 2% |  | 55847.5311
1.3 | PCC |  |  |  | 10% |  | 279237.6557
1.4 | Footings - 102 nos |  |  |  | 30%
1.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 293199.5384
1.4.2 | Shuttering |  |  |  | 6% |  | 167542.5934
1.4.3 | Concrete |  |  |  | 13.5% |  | 376970.8351
1.5 | Column - 102 nos |  |  |  | 25%
1.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 314142.3626
1.5.2 | Shuttering |  |  |  | 6.25% |  | 174523.5348
1.5.3 | Concrete |  |  |  | 7.5% |  | 209428.2417
1.6 | Backfilling |  |  |  | 3% |  | 83771.2967
1.7 | Plinth beam |  |  |  | 25%
1.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 349047.0696
1.7.2 | Shuttering |  |  |  | 5% |  | 139618.8278
1.7.3 | Concrete |  |  |  | 7.5% |  | 209428.2417
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 7355616.3296
2.1 | Excavation |  |  |  | 5% |  | 367780.8165
2.2 | ATT |  |  |  | 2% |  | 147112.3266
2.3 | PCC |  |  |  | 10% |  | 735561.633
2.4 | Footings - 272 nos |  |  |  | 30%
2.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 772339.7146
2.4.2 | Shuttering |  |  |  | 6% |  | 441336.9798
2.4.3 | Concrete |  |  |  | 13.5% |  | 993008.2045
2.5 | Column - 272 nos |  |  |  | 25%
2.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 827506.8371
2.5.2 | Shuttering |  |  |  | 6.25% |  | 459726.0206
2.5.3 | Concrete |  |  |  | 7.5% |  | 551671.2247
2.6 | Backfilling |  |  |  | 3% |  | 220668.4899
2.7 | Plinth beam |  |  |  | 25%
2.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 919452.0412
2.7.2 | Shuttering |  |  |  | 5% |  | 367780.8165
2.7.3 | Concrete |  |  |  | 7.5% |  | 551671.2247
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 1103426.9723
3.1 | Excavation |  |  |  | 5% |  | 55171.3486
3.2 | ATT |  |  |  | 2% |  | 22068.5394
3.3 | PCC |  |  |  | 10% |  | 110342.6972
3.4 | Footings - 42 nos |  |  |  | 30%
3.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 115859.8321
3.4.2 | Shuttering |  |  |  | 6% |  | 66205.6183
3.4.3 | Concrete |  |  |  | 13.5% |  | 148962.6413
3.5 | Column - 42 nos |  |  |  | 25%
3.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 124135.5344
3.5.2 | Shuttering |  |  |  | 6.25% |  | 68964.1858
3.5.3 | Concrete |  |  |  | 7.5% |  | 82757.0229
3.6 | Backfilling |  |  |  | 3% |  | 33102.8092
3.7 | Plinth beam |  |  |  | 25%
3.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 137928.3715
3.7.2 | Shuttering |  |  |  | 5% |  | 55171.3486
3.7.3 | Concrete |  |  |  | 7.5% |  | 82757.0229
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 12325631.336
4.1 | Excavation |  |  |  | 5% |  | 616281.5668
4.2 | ATT |  |  |  | 2% |  | 246512.6267
4.3 | PCC |  |  |  | 10% |  | 1232563.1336
4.4 | Footings - 223 nos |  |  |  | 30%
4.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 1294191.2903
4.4.2 | Shuttering |  |  |  | 6% |  | 739537.8802
4.4.3 | Concrete |  |  |  | 13.5% |  | 1663960.2304
4.5 | Column - 223 nos |  |  |  | 25%
4.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 1386633.5253
4.5.2 | Shuttering |  |  |  | 6.25% |  | 770351.9585
4.5.3 | Concrete |  |  |  | 7.5% |  | 924422.3502
4.6 | Backfilling |  |  |  | 3% |  | 369768.9401
4.7 | Plinth beam |  |  |  | 25%
4.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 1540703.917
4.7.2 | Shuttering |  |  |  | 5% |  | 616281.5668
4.7.3 | Concrete |  |  |  | 7.5% |  | 924422.3502
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 1367064.6562
5.1 | Excavation |  |  |  | 5% |  | 68353.2328
5.2 | ATT |  |  |  | 2% |  | 27341.2931
5.3 | PCC |  |  |  | 10% |  | 136706.4656
5.4 | Footings - 09 nos |  |  |  | 30%
5.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 143541.7889
5.4.2 | Shuttering |  |  |  | 6% |  | 82023.8794
5.4.3 | Concrete |  |  |  | 13.5% |  | 184553.7286
5.5 | Column - 09 nos |  |  |  | 25%
5.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 153794.7738
5.5.2 | Shuttering |  |  |  | 6.25% |  | 85441.541
5.5.3 | Concrete |  |  |  | 7.5% |  | 102529.8492
5.6 | Backfilling |  |  |  | 3% |  | 41011.9397
5.7 | Plinth beam |  |  |  | 25%
5.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 170883.082
5.7.2 | Shuttering |  |  |  | 5% |  | 68353.2328
5.7.3 | Concrete |  |  |  | 7.5% |  | 102529.8492
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 5041969.6461
6.1 | Excavation |  |  |  | 5% |  | 252098.4823
6.2 | ATT |  |  |  | 2% |  | 100839.3929
6.3 | PCC |  |  |  | 10% |  | 504196.9646
6.4 | Footings - 152 nos |  |  |  | 30%
6.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 529406.8128
6.4.2 | Shuttering |  |  |  | 6% |  | 302518.1788
6.4.3 | Concrete |  |  |  | 13.5% |  | 680665.9022
6.5 | Column - 152 nos |  |  |  | 25%
6.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 567221.5852
6.5.2 | Shuttering |  |  |  | 6.25% |  | 315123.1029
6.5.3 | Concrete |  |  |  | 7.5% |  | 378147.7235
6.6 | Backfilling |  |  |  | 3% |  | 151259.0894
6.7 | Plinth beam |  |  |  | 25%
6.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 630246.2058
6.7.2 | Shuttering |  |  |  | 5% |  | 252098.4823
6.7.3 | Concrete |  |  |  | 7.5% |  | 378147.7235
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 4273914.5032
7.1 | Excavation |  |  |  | 5% |  | 213695.7252
7.2 | ATT |  |  |  | 2% |  | 85478.2901
7.3 | PCC |  |  |  | 10% |  | 427391.4503
7.4 | Footings - 148 nos |  |  |  | 30%
7.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 448761.0228
7.4.2 | Shuttering |  |  |  | 6% |  | 256434.8702
7.4.3 | Concrete |  |  |  | 13.5% |  | 576978.4579
7.5 | Column - 148 nos |  |  |  | 25%
7.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 480815.3816
7.5.2 | Shuttering |  |  |  | 6.25% |  | 267119.6565
7.5.3 | Concrete |  |  |  | 7.5% |  | 320543.5877
7.6 | Backfilling |  |  |  | 3% |  | 128217.4351
7.7 | Plinth beam |  |  |  | 25%
7.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 534239.3129
7.7.2 | Shuttering |  |  |  | 5% |  | 213695.7252
7.7.3 | Concrete |  |  |  | 7.5% |  | 320543.5877
B | On Completion Civil Structural work [Superstructure] |  |  | 6% |  | 68520000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 5584753.1131
1.1 | Column - 102 nos |  |  |  | 25%
1.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 628284.7252
1.1.2 | Shuttering |  |  |  | 6.25% |  | 349047.0696
1.1.3 | Concrete |  |  |  | 7.5% |  | 418856.4835
1.2 | Roof Slab |  |  |  | 45%
1.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 954992.7823
1.2.2 | Shuttering |  |  |  | 13.5% |  | 753941.6703
1.2.3 | Concrete |  |  |  | 14.4% |  | 804204.4483
1.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 1675425.9339
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 14711232.6592
2.1 | Column - 272 nos |  |  |  | 25%
2.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 1655013.6742
2.1.2 | Shuttering |  |  |  | 6.25% |  | 919452.0412
2.1.3 | Concrete |  |  |  | 7.5% |  | 1103342.4494
2.2 | Roof Slab |  |  |  | 45%
2.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 2515620.7847
2.2.2 | Shuttering |  |  |  | 13.5% |  | 1986016.409
2.2.3 | Concrete |  |  |  | 14.4% |  | 2118417.5029
2.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 4413369.7978
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 2206853.9445
3.1 | Column - 42 nos |  |  |  | 25%
3.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 248271.0688
3.1.2 | Shuttering |  |  |  | 6.25% |  | 137928.3715
3.1.3 | Concrete |  |  |  | 7.5% |  | 165514.0458
3.2 | Roof Slab |  |  |  | 45%
3.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 377372.0245
3.2.2 | Shuttering |  |  |  | 13.5% |  | 297925.2825
3.2.3 | Concrete |  |  |  | 14.4% |  | 317786.968
3.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 662056.1834
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 24651262.672
4.1 | Column - 223 nos |  |  |  | 25%
4.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 2773267.0506
4.1.2 | Shuttering |  |  |  | 6.25% |  | 1540703.917
4.1.3 | Concrete |  |  |  | 7.5% |  | 1848844.7004
4.2 | Roof Slab |  |  |  | 45%
4.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 4215365.9169
4.2.2 | Shuttering |  |  |  | 13.5% |  | 3327920.4607
4.2.3 | Concrete |  |  |  | 14.4% |  | 3549781.8248
4.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 7395378.8016
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 2734129.3125
5.1 | Column - 09 nos |  |  |  | 27%
I] Ground Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
II] First Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
III] Second Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
IV] Third Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
V] Fourth Floor
5.1.1 | Supply of Reinforcement |  |  |  | 3.5% |  | 95694.5259
5.1.2 | Shuttering |  |  |  | 1.75% |  | 47847.263
5.1.3 | Concrete |  |  |  | 2.75% |  | 75188.5561
5.2 | Roof Slab/ Staircase |  |  |  | 48%
I] Ground Floor
5.2.1 | Supply of Reinforcement |  |  |  | 2% |  | 54682.5862
5.2.2 | Shuttering |  |  |  | 1.5% |  | 41011.9397
5.2.3 | Concrete |  |  |  | 2.5% |  | 68353.2328
II] First Floor
5.2.1 | Supply of Reinforcement |  |  |  | 2% |  | 54682.5862
5.2.2 | Shuttering |  |  |  | 1.5% |  | 41011.9397
5.2.3 | Concrete |  |  |  | 2.5% |  | 68353.2328
III] Second Floor
5.2.1 | Supply of Reinforcement |  |  |  | 2% |  | 54682.5862
5.2.2 | Shuttering |  |  |  | 1.5% |  | 41011.9397
5.2.3 | Concrete |  |  |  | 2.5% |  | 68353.2328
IV] Third Floor
5.2.1 | Supply of Reinforcement |  |  |  | 3.5% |  | 95694.5259
5.2.2 | Shuttering |  |  |  | 2.75% |  | 75188.5561
5.2.3 | Concrete |  |  |  | 4.5% |  | 123035.8191
V] Fourth Floor
5.2.1 | Supply of Reinforcement |  |  |  | 6.25% |  | 170883.082
5.2.2 | Shuttering |  |  |  | 5.5% |  | 150377.1122
5.2.3 | Concrete |  |  |  | 7.5% |  | 205059.6984
5.3 | Brick work with Ornamental/ Decorative |  |  |  | 25%
| I] Ground Floor |  |  |  | 8.5% |  | 232400.9916
| II] First Floor |  |  |  | 3.5% |  | 95694.5259
| III] Second Floor |  |  |  | 3.5% |  | 95694.5259
| IV] Third Floor |  |  |  | 3.5% |  | 95694.5259
| V] Fourth Floor |  |  |  | 6% |  | 164047.7587
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 10083939.2922
6.1 | Column - 152 nos |  |  |  | 25%
6.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 1134443.1704
6.1.2 | Shuttering |  |  |  | 6.25% |  | 630246.2058
6.1.3 | Concrete |  |  |  | 7.5% |  | 756295.4469
6.2 | Roof Slab |  |  |  | 45%
6.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 1724353.619
6.2.2 | Shuttering |  |  |  | 13.5% |  | 1361331.8044
6.2.3 | Concrete |  |  |  | 14.4% |  | 1452087.2581
6.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 3025181.7877
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 8547829.0064
7.1 | Column - 148 nos |  |  |  | 25%
7.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 961630.7632
7.1.2 | Shuttering |  |  |  | 6.25% |  | 534239.3129
7.1.3 | Concrete |  |  |  | 7.5% |  | 641087.1755
7.2 | Roof Slab |  |  |  | 45%
7.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 1461678.7601
7.2.2 | Shuttering |  |  |  | 13.5% |  | 1153956.9159
7.2.3 | Concrete |  |  |  | 14.4% |  | 1230887.3769
7.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 2564348.7019
C | On Completion Khandolite masonry |  |  | 7% |  | 79940000
1 | Information counter | 127.89 | Cum |  | 14.35% |  |  | 11468038.094
1.1 | Supply of Khandolite stone |  |  |  | 70% |  | 8027626.6658
1.2 | Sizing work for required shape |  |  |  | 15% |  | 1720205.7141
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 1720205.7141
2 | Vending zone | 312.92 | Cum |  | 35.1% |  |  | 28059883.3401
2.1 | Supply of Khandolite stone |  |  |  | 70% |  | 19641918.338
2.2 | Sizing work for required shape |  |  |  | 15% |  | 4208982.501
2.3 | Laying and Fixing charge |  |  |  | 15% |  | 4208982.501
3 | Shoe store | 50.32 | Cum |  | 5.645% |  |  | 4512250.1907
3.1 | Supply of Khandolite stone |  |  |  | 70% |  | 3158575.1335
3.2 | Sizing work for required shape |  |  |  | 15% |  | 676837.5286
3.3 | Laying and Fixing charge |  |  |  | 15% |  | 676837.5286
4 | Clock tower | 14.26 | Cum |  | 1.6% |  |  | 1278710.0103
4.1 | Supply of Khandolite stone |  |  |  | 70% |  | 895097.0072
4.2 | Sizing work for required shape |  |  |  | 15% |  | 191806.5015
4.3 | Laying and Fixing charge |  |  |  | 15% |  | 191806.5015
5 | Religious Facilities | 201.78 | Cum |  | 22.63% |  |  | 18093836.3171
5.1 | Supply of Khandolite stone |  |  |  | 70% |  | 12665685.422
5.2 | Sizing work for required shape |  |  |  | 15% |  | 2714075.4476
5.3 | Laying and Fixing charge |  |  |  | 15% |  | 2714075.4476
6 | Pilgrim Facility | 184.31 | Cum |  | 20.67% |  |  | 16527282.0478
5.1 | Supply of Khandolite stone |  |  |  | 70% |  | 11569097.4335
5.2 | Sizing work for required shape |  |  |  | 15% |  | 2479092.3072
5.3 | Laying and Fixing charge |  |  |  | 15% |  | 2479092.3072
D | On completion of finishing work such as flooring, plastering, painting and other finishing works |  |  | 4% |  | 45680000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 3723168.7421
1.1 | Joineries work |  |  |  | 15%
1.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Roofing Shingles& Wood items |  |  |  | 10.5% |  | 390932.7179
1.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 167542.5934
1.2 | Plastering |  |  |  | 50%
1.2.1 | Ceiling |  |  |  | 12.5% |  | 465396.0928
1.2.2 | Internal |  |  |  | 20% |  | 744633.7484
1.2.3 | External |  |  |  | 17.5% |  | 651554.5299
1.3 | Flooring |  |  |  | 25%
1.3.1 | Supply of materials |  |  |  | 17.5% |  | 651554.5299
1.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 279237.6557
1.4 | Painting |  |  |  | 10%
1.4.1 | Ceiling |  |  |  | 2.5% |  | 93079.2186
1.4.2 | Internal |  |  |  | 4% |  | 148926.7497
1.4.3 | External |  |  |  | 3.5% |  | 130310.906
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 9807488.4395
2.1 | Joineries work |  |  |  | 15%
2.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Roofing Shingles& Wood items |  |  |  | 10.5% |  | 1029786.2861
2.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 441336.9798
2.2 | Plastering |  |  |  | 50%
2.2.1 | Ceiling |  |  |  | 12.5% |  | 1225936.0549
2.2.2 | Internal |  |  |  | 20% |  | 1961497.6879
2.2.3 | External |  |  |  | 17.5% |  | 1716310.4769
2.3 | Flooring |  |  |  | 25%
2.3.1 | Supply of materials |  |  |  | 17.5% |  | 1716310.4769
2.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 735561.633
2.4 | Painting |  |  |  | 10%
2.4.1 | Ceiling |  |  |  | 2.5% |  | 245187.211
2.4.2 | Internal |  |  |  | 4% |  | 392299.5376
2.4.3 | External |  |  |  | 3.5% |  | 343262.0954
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 1471235.963
3.1 | Joineries work |  |  |  | 15%
3.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 154479.7761
3.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 66205.6183
3.2 | Plastering |  |  |  | 50%
3.2.1 | Ceiling |  |  |  | 12.5% |  | 183904.4954
3.2.2 | Internal |  |  |  | 20% |  | 294247.1926
3.2.3 | External |  |  |  | 17.5% |  | 257466.2935
3.3 | Flooring |  |  |  | 25%
3.3.1 | Supply of materials |  |  |  | 17.5% |  | 257466.2935
3.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 110342.6972
3.4 | Painting |  |  |  | 10%
3.4.1 | Ceiling |  |  |  | 2.5% |  | 36780.8991
3.4.2 | Internal |  |  |  | 4% |  | 58849.4385
3.4.3 | External |  |  |  | 3.5% |  | 51493.2587
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 16434175.1147
4.1 | Joineries work |  |  |  | 15%
4.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 1725588.387
4.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 739537.8802
4.2 | Plastering |  |  |  | 50%
4.2.1 | Ceiling |  |  |  | 12.5% |  | 2054271.8893
4.2.2 | Internal |  |  |  | 20% |  | 3286835.0229
4.2.3 | External |  |  |  | 17.5% |  | 2875980.6451
4.3 | Flooring |  |  |  | 25%
4.3.1 | Supply of materials |  |  |  | 17.5% |  | 2875980.6451
4.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 1232563.1336
4.4 | Painting |  |  |  | 10%
4.4.1 | Ceiling |  |  |  | 2.5% |  | 410854.3779
4.4.2 | Internal |  |  |  | 4% |  | 657367.0046
4.4.3 | External |  |  |  | 3.5% |  | 575196.129
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 1822752.875
5.1 | Joineries work |  |  |  | 25%
I] Ground Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 5.5% |  | 100251.4081
5.1.2 | Fixing and Finishing |  |  |  | 1.5% |  | 27341.2931
II] First Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
III] Second Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
IV] Third Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
V] Fourth Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
5.2 | Plastering |  |  |  | 40%
I] Ground Floor
5.2.1 | Ceiling |  |  |  | 1.5% |  | 27341.2931
5.2.2 | Internal |  |  |  | 2.5% |  | 45568.8219
5.2.3 | External |  |  |  | 2.5% |  | 45568.8219
II] First Floor
5.2.1 | Ceiling |  |  |  | 1.5% |  | 27341.2931
5.2.2 | Internal |  |  |  | 2.5% |  | 45568.8219
5.2.3 | External |  |  |  | 2.5% |  | 45568.8219
III] Second Floor
5.2.1 | Ceiling |  |  |  | 1.5% |  | 27341.2931
5.2.2 | Internal |  |  |  | 2.5% |  | 45568.8219
5.2.3 | External |  |  |  | 2.5% |  | 45568.8219
IV] Third Floor
5.2.1 | Ceiling |  |  |  | 2.5% |  | 45568.8219
5.2.2 | Internal |  |  |  | 2.75% |  | 50125.7041
5.2.3 | External |  |  |  | 2.75% |  | 50125.7041
V] Fourth Floor
5.2.1 | Ceiling |  |  |  | 3% |  | 54682.5862
5.2.2 | Internal |  |  |  | 5.25% |  | 95694.5259
5.2.3 | External |  |  |  | 4.25% |  | 77466.9972
5.3 | Flooring |  |  |  | 25%
I] Ground Floor
5.3.1 | Supply of materials |  |  |  | 5.25% |  | 95694.5259
5.3.2 | Laying and Leveling |  |  |  | 2% |  | 36455.0575
II] First Floor
5.3.1 | Supply of materials |  |  |  | 3% |  | 54682.5862
5.3.2 | Laying and Leveling |  |  |  | 1.25% |  | 22784.4109
III] Second Floor
5.3.1 | Supply of materials |  |  |  | 3% |  | 54682.5862
5.3.2 | Laying and Leveling |  |  |  | 1.25% |  | 22784.4109
IV] Third Floor
5.3.1 | Supply of materials |  |  |  | 3% |  | 54682.5862
5.3.2 | Laying and Leveling |  |  |  | 1.25% |  | 22784.4109
V] Fourth Floor
5.3.1 | Supply of materials |  |  |  | 3.5% |  | 63796.3506
5.3.2 | Laying and Leveling |  |  |  | 1.5% |  | 27341.2931
5.4 | Painting |  |  |  | 10%
I] Ground Floor
5.4.1 | Ceiling |  |  |  | 0.4% |  | 7291.0115
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
II] First Floor
5.4.1 | Ceiling |  |  |  | 0.4% |  | 7291.0115
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
III] Second Floor
5.4.1 | Ceiling |  |  |  | 0.4% |  | 7291.0115
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
IV] Third Floor
5.4.1 | Ceiling |  |  |  | 0.6% |  | 10936.5172
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
V] Fourth Floor
5.4.1 | Ceiling |  |  |  | 0.7% |  | 12759.2701
5.4.2 | Internal |  |  |  | 1.4% |  | 25518.5402
5.4.3 | External |  |  |  | 1.1% |  | 20050.2816
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 6722626.1948
6.1 | Joineries work |  |  |  | 15%
6.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 705875.7505
6.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 302518.1788
6.2 | Plastering |  |  |  | 50%
6.2.1 | Ceiling |  |  |  | 12.5% |  | 840328.2743
6.2.2 | Internal |  |  |  | 20% |  | 1344525.239
6.2.3 | External |  |  |  | 17.5% |  | 1176459.5841
6.3 | Flooring |  |  |  | 25%
6.3.1 | Supply of materials |  |  |  | 17.5% |  | 1176459.5841
6.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 504196.9646
6.4 | Painting |  |  |  | 10%
6.4.1 | Ceiling |  |  |  | 2.5% |  | 168065.6549
6.4.2 | Internal |  |  |  | 4% |  | 268905.0478
6.4.3 | External |  |  |  | 3.5% |  | 235291.9168
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 5698552.671
7.1 | Joineries work |  |  |  | 15%
7.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 598348.0305
7.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 256434.8702
7.2 | Plastering |  |  |  | 50%
7.2.1 | Ceiling |  |  |  | 12.5% |  | 712319.0839
7.2.2 | Internal |  |  |  | 20% |  | 1139710.5342
7.2.3 | External |  |  |  | 17.5% |  | 997246.7174
7.3 | Flooring |  |  |  | 25%
7.3.1 | Supply of materials |  |  |  | 17.5% |  | 997246.7174
7.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 427391.4503
7.4 | Painting |  |  |  | 10%
7.4.1 | Ceiling |  |  |  | 2.5% |  | 142463.8168
7.4.2 | Internal |  |  |  | 4% |  | 227942.1068
7.4.3 | External |  |  |  | 3.5% |  | 199449.3435
E | Internal Water supply & Sanitary Installation |  |  | 1% |  | 11420000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 930792.1855
1.1 | Supply of Materials |  |  |  | 70% |  | 651554.5299
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 186158.4371
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 93079.2186
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 2451872.1099
2.1 | Supply of Materials |  |  |  | 70% |  | 1716310.4769
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 490374.422
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 245187.211
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 367808.9908
3.1 | Supply of Materials |  |  |  | 70% |  | 257466.2935
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 73561.7982
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 36780.8991
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 4108543.7787
4.1 | Supply of Materials |  |  |  | 70% |  | 2875980.6451
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 821708.7557
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 410854.3779
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 455688.2187
5.1 | Supply of Materials |  |  |  | 70% |  | 318981.7531
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 91137.6437
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 45568.8219
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 1680656.5487
6.1 | Supply of Materials |  |  |  | 70% |  | 1176459.5841
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 336131.3097
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 168065.6549
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 1424638.1677
7.1 | Supply of Materials |  |  |  | 70% |  | 997246.7174
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 284927.6335
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 142463.8168
F | External Water supply & Sanitary Installation |  |  | 0.5% |  | 5710000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 465396.0928
1.1 | Supply of Materials |  |  |  | 70% |  | 325777.2649
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 93079.2186
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 46539.6093
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 1225936.0549
2.1 | Supply of Materials |  |  |  | 70% |  | 858155.2385
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 245187.211
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 122593.6055
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 183904.4954
3.1 | Supply of Materials |  |  |  | 70% |  | 128733.1468
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 36780.8991
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 18390.4495
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 2054271.8893
4.1 | Supply of Materials |  |  |  | 70% |  | 1437990.3225
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 410854.3779
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 205427.1889
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 227844.1094
5.1 | Supply of Materials |  |  |  | 70% |  | 159490.8766
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 45568.8219
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 22784.4109
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 840328.2743
6.1 | Supply of Materials |  |  |  | 70% |  | 588229.792
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 168065.6549
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 84032.8274
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 712319.0839
7.1 | Supply of Materials |  |  |  | 70% |  | 498623.3587
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 142463.8168
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 71231.9084
G | Internal electric Installations |  |  | 1% |  | 11420000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 930792.1855
1.1 | Supply of Materials |  |  |  | 70% |  | 651554.5299
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 186158.4371
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 93079.2186
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 2451872.1099
2.1 | Supply of Materials |  |  |  | 70% |  | 1716310.4769
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 490374.422
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 245187.211
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 367808.9908
3.1 | Supply of Materials |  |  |  | 70% |  | 257466.2935
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 73561.7982
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 36780.8991
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 4108543.7787
4.1 | Supply of Materials |  |  |  | 70% |  | 2875980.6451
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 821708.7557
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 410854.3779
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 455688.2187
5.1 | Supply of Materials |  |  |  | 70% |  | 318981.7531
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 91137.6437
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 45568.8219
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 1680656.5487
6.1 | Supply of Materials |  |  |  | 70% |  | 1176459.5841
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 336131.3097
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 168065.6549
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 1424638.1677
7.1 | Supply of Materials |  |  |  | 70% |  | 997246.7174
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 284927.6335
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 142463.8168
H | External electric Installations |  |  | 0.5% |  | 5710000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 465396.0928
1.1 | Supply of Materials |  |  |  | 70% |  | 325777.2649
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 93079.2186
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 46539.6093
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 1225936.0549
2.1 | Supply of Materials |  |  |  | 70% |  | 858155.2385
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 245187.211
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 122593.6055
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 183904.4954
3.1 | Supply of Materials |  |  |  | 70% |  | 128733.1468
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 36780.8991
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 18390.4495
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 2054271.8893
4.1 | Supply of Materials |  |  |  | 70% |  | 1437990.3225
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 410854.3779
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 205427.1889
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 227844.1094
5.1 | Supply of Materials |  |  |  | 70% |  | 159490.8766
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 45568.8219
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 22784.4109
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 840328.2743
6.1 | Supply of Materials |  |  |  | 70% |  | 588229.792
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 168065.6549
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 84032.8274
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 712319.0839
7.1 | Supply of Materials |  |  |  | 70% |  | 498623.3587
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 142463.8168
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 71231.9084
2.2 | Foot over Bridge & QMS
A | On Completion up to Plinth |  |  | 2% |  | 22840000
1 | Foot over Bridge | 666 | Sqm |  | 27.41% |  |  | 6259851.8519
1.1 | Excavation |  |  |  | 5% |  | 312992.5926
1.2 | Supply of Reinforcement |  |  |  | 50% |  | 3129925.9259
1.3 | Shuttering work |  |  |  | 15% |  | 938977.7778
1.4 | Concrete works |  |  |  | 25% |  | 1564962.963
1.5 | Backfilling |  |  |  | 5% |  | 312992.5926
2 | Que Management System | 1764 | Sqm |  | 72.59% |  |  | 16580148.1481
2.1 | Excavation |  |  |  | 5% |  | 829007.4074
2.2 | Supply of Reinforcement |  |  |  | 50% |  | 8290074.0741
2.3 | Shuttering work |  |  |  | 15% |  | 2487022.2222
2.4 | Concrete works |  |  |  | 25% |  | 4145037.037
2.5 | Backfilling |  |  |  | 5% |  | 829007.4074
B | On Completion Civil Structural work |  |  | 3% |  | 34260000
1 | Foot over Bridge | 666 | Sqm |  | 27.41% |  |  | 9389777.7778
1.1 | Supply of Reinforcement |  |  |  | 20% |  | 1877955.5556
1.2 | Shuttering |  |  |  | 10% |  | 938977.7778
1.3 | Concrete |  |  |  | 15% |  | 1408466.6667
1.4 | Supply of Structural steel |  |  |  | 40% |  | 3755911.1111
1.4.1 | Structural steel Assemblying and Erection |  |  |  | 15% |  | 1408466.6667
2 | Que Management System | 1764 | Sqm |  | 72.59% |  |  | 24870222.2222
2.1 | Supply of Reinforcement |  |  |  | 20% |  | 4974044.4444
2.2 | Shuttering |  |  |  | 10% |  | 2487022.2222
2.3 | Concrete |  |  |  | 15% |  | 3730533.3333
2.4 | Supply of Structural steel |  |  |  | 40% |  | 9948088.8889
2.4.1 | Structural steel Assemblying and Erection |  |  |  | 15% |  | 3730533.3333
C | On completion of finishing work such as roofing, flooring, plastering, painting, NFC cladding and other finishing works |  |  | 3% |  | 34260000
1 | Foot over Bridge | 666 | Sqm |  | 27.41% |  |  | 9389777.7778
1.1 | Supply of Granite |  |  |  | 43% |  | 4037604.4444
1.1.1 | Laying and Fixing |  |  |  | 17% |  | 1596262.2222
1.2 | Supply of 23mm Tks wood polymer composite |  |  |  | 28% |  | 2629137.7778
1.2.1 | Laying and Fixing |  |  |  | 12% |  | 1126773.3333
2 | Que Management System | 1764 | Sqm |  | 72.59% |  |  | 24870222.2222
2.1 | Supply of Khandolite stone |  |  |  | 25% |  | 6217555.5556
2.1.1 | Sizing work for required shape |  |  |  | 3% |  | 746106.6667
2.1.2 | Laying and Fixing |  |  |  | 2% |  | 497404.4444
2.2 | Supply of SS handrail |  |  |  | 20% |  | 4974044.4444
2.2.1 | Laying and Fixing |  |  |  | 5% |  | 1243511.1111
2.3 | Supply of Multi wall Polycarbonate sheet |  |  |  | 15% |  | 3730533.3333
2.3.1 | Laying and Fixing |  |  |  | 5% |  | 1243511.1111
2.4 | Supply of NFC wood material. |  |  |  | 15% |  | 3730533.3333
2.4.1 | Laying and Fixing |  |  |  | 5% |  | 1243511.1111
2.5 | Supply of Landscapping. |  |  |  | 3% |  | 746106.6667
2.5.1 | Laying work |  |  |  | 2% |  | 497404.4444
2.3 | Compound wall & Heritage Gate
A | On Completion up to Plinth |  |  | 0.5% |  | 5710000
1 | Compound wall | 910 | Mtr |  | 94.99% |  |  | 5423903.9666
1.1 | Excavation |  |  |  | 10% |  | 542390.3967
1.2 | Supply of Reinforcement |  |  |  | 40% |  | 2169561.5866
1.3 | Shuttering work |  |  |  | 20% |  | 1084780.7933
1.4 | Concrete works |  |  |  | 25% |  | 1355975.9916
1.5 | Backfilling |  |  |  | 5% |  | 271195.1983
2 | Heritage Gate | 48 | Mtr |  | 5.01% |  |  | 286096.0334
2.1 | Excavation |  |  |  | 10% |  | 28609.6033
2.2 | Supply of Reinforcement |  |  |  | 40% |  | 114438.4134
2.3 | Shuttering work |  |  |  | 20% |  | 57219.2067
2.4 | Concrete works |  |  |  | 25% |  | 71524.0084
2.5 | Backfilling |  |  |  | 5% |  | 14304.8017
B | On Completion Civil Structural work |  |  | 2% |  | 22840000
1 | Compound wall | 910 | Mtr |  | 94.99% |  |  | 21695615.8664
1.1 | Supply of Reinforcement |  |  |  | 25% |  | 5423903.9666
1.2 | Shuttering |  |  |  | 8% |  | 1735649.2693
1.3 | Concrete |  |  |  | 13% |  | 2820430.0626
1.4 | Brick work with Ornamental/ Decorative |  |  |  | 14% |  | 3037386.2213
1.5 | Supply of Structural steel - Grill |  |  |  | 40% |  | 8678246.3466
2 | Heritage Gate | 48 | Mtr |  | 5.01% |  |  | 1144384.1336
2.1 | Supply of Reinforcement |  |  |  | 15% |  | 171657.62
2.2 | Shuttering |  |  |  | 7% |  | 80106.8894
2.3 | Concrete |  |  |  | 9% |  | 102994.572
2.4 | Brick work with Ornamental/ Decorative |  |  |  | 14% |  | 160213.7787
2.5 | Supply of Structural steel - Gate |  |  |  | 55% |  | 629411.2735
C | On completion of finishing work such as carving, plastering, painting and other finishing works |  |  | 0.5% |  | 5710000
1 | Compound wall | 910 | Mtr |  | 94.99% |  |  | 5423903.9666
1.1 | Supply of Khandolite stone |  |  |  | 60% |  | 3254342.38
1.1.1 | Sizing work for required shape |  |  |  | 15% |  | 813585.595
1.1.2 | Laying and Fixing |  |  |  | 10% |  | 542390.3967
1.2 | Plastering |  |  |  | 10% |  | 542390.3967
1.3 | Painting |  |  |  | 5% |  | 271195.1983
2 | Heritage Gate | 48 | Mtr |  | 5.01% |  |  | 286096.0334
2.1 | Supply of Khandolite stone |  |  |  | 52% |  | 148769.9374
2.1.1 | Sizing work for required shape |  |  |  | 15% |  | 42914.405
2.1.2 | Laying and Fixing |  |  |  | 10% |  | 28609.6033
2.2 | Plastering |  |  |  | 15% |  | 42914.405
2.3 | Painting |  |  |  | 8% |  | 22887.6827
2.4 | River front development
A | On Completion of structural work upto formation ground level . |  |  | 5% |  | 57100000 |  | 57100000
1.1 | Excavation |  |  |  | 2.5% |  | 1427500
1.2 | Supply of Reinforcement |  |  |  | 40% |  | 22840000
1.3 | Shuttering work |  |  |  | 24% |  | 13704000
1.4 | Concrete works |  |  |  | 32% |  | 18272000
1.5 | Filling work |  |  |  | 1.5% |  | 856500
B | On Completion Civil Structural work |  |  | 5% |  | 57100000 |  | 57100000
1.1 | Supply of Reinforcement |  |  |  | 40% |  | 22840000
1.2 | Shuttering |  |  |  | 20% |  | 11420000
1.3 | Concrete |  |  |  | 40% |  | 22840000
C | On Completion Paving. |  |  | 5% |  | 57100000 |  | 57100000
1.1 | Supply of Materials |  |  |  | 70% |  | 39970000
1.2 | Laying and Fixing |  |  |  | 30% |  | 17130000
D | On completion of finishing work such as plastering, painting and other finishing works |  |  | 1% |  | 11420000 |  | 11420000
1.1 | Brick work |  |  |  | 45% |  | 5139000
1.2 | Plastering |  |  |  | 45% |  | 5139000
1.3 | Painting |  |  |  | 10% |  | 1142000
2.5 | Parking
A | On Completion Foundation plinth | 23000 | Sqm | 0.3% |  | 3426000 |  | 3426000
1.1 | Excavation |  |  |  | 15% |  | 513900
1.2 | Shuttering work |  |  |  | 25% |  | 856500
1.3 | Concrete works |  |  |  | 60% |  | 2055600
B | On Completion Subbase & Base | 23000 | Sqm | 1% |  | 11420000 |  | 11420000
1.1 | Excavation; Filling and Ramping work |  |  |  | 30% |  | 3426000
1.2 | Subbase work |  |  |  | 70% |  | 7994000
C | On Completion Paving . | 23000 | Sqm | 1.5% |  | 17130000 |  | 17130000
1.1 | Supply of Materials |  |  |  | 70% |  | 11991000
1.2 | Laying and Fixing |  |  |  | 30% |  | 5139000
D | On completion of finishing work such as plastering, painting and other finishing works | 23000 | Sqm | 0.2% |  | 2284000 |  | 2284000
1.1 | Brick work |  |  |  | 45% |  | 1027800
1.2 | Plastering |  |  |  | 40% |  | 913600
1.3 | Painting |  |  |  | 15% |  | 342600
2.6 | Pathway/Walkway
A | On Completion Foundation plinth . |  | Sqm | 1% |  | 11420000 |  | 11420000
1.1 | Excavation |  |  |  | 15% |  | 1713000
1.2 | Shuttering work |  |  |  | 25% |  | 2855000
1.3 | Concrete works |  |  |  | 60% |  | 6852000
B | On Completion Subbase & Base . |  | Sqm | 2% |  | 22840000 |  | 22840000
1.1 | Excavation; Filling and Ramping work |  |  |  | 30% |  | 6852000
1.2 | Subbase work |  |  |  | 70% |  | 15988000
C | On Completion Paving . |  | Sqm | 13% |  | 148460000 |  | 148460000
1.1 | Supply of Khandolite stone/Square granite cobbles |  |  |  | 70% |  | 103922000
1.2 | Sizing work for required shape |  |  |  | 15% |  | 22269000
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 22269000
D | On completion of finishing work such as plastering, painting and other finishing works |  | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Brick work |  |  |  | 40% |  | 2284000
1.2 | Plastering |  |  |  | 25% |  | 1427500
1.3 | Applying of Nitocote wall guard |  |  |  | 20% |  | 1142000
1.4 | Painting |  |  |  | 15% |  | 856500
2.7 | Heritage corridor
A | On Completion of drain . [900 Rmt] | 900 | Rmt | 1.2% |  | 13704000 |  | 13704000
1.1 | Excavation |  |  |  | 15% |  | 2055600
1.2 | Supply of Reinforcement |  |  |  | 10% |  | 1370400
1.3 | Shuttering work |  |  |  | 10% |  | 1370400
1.4 | Concrete works |  |  |  | 15% |  | 2055600
1.5 | Brick work |  |  |  | 50% |  | 6852000
B | On Completion Subbase & Base . | 18000 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Excavation; Filling and Ramping work |  |  |  | 30% |  | 1713000
1.2 | Subbase work |  |  |  | 70% |  | 3997000
C | On Completion Paving . | 18000 | Sqm | 3.5% |  | 39970000 |  | 39970000
1.1 | Supply of Natural Square granite cobbles |  |  |  | 70% |  | 27979000
1.2 | Sizing work for required shape |  |  |  | 15% |  | 5995500
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 5995500
D | On completion of finishing work such as plastering, painting and other finishing works | 18000 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Plastering |  |  |  | 90% |  | 5139000
1.2 | Painting |  |  |  | 10% |  | 571000
2.8 | Waterbody and Sitouts
A | On Completion Foundation and sub structure . | 632 | Sqm | 0.25% |  | 2855000 |  | 2855000
1.1 | Excavation |  |  |  | 15% |  | 428250
1.2 | Supply of Reinforcement |  |  |  | 40% |  | 1142000
1.3 | Shuttering work |  |  |  | 20% |  | 571000
1.4 | Concrete works |  |  |  | 25% |  | 713750
B | On Completion Paving/sitouts . | 632 | Sqm | 0.75% |  | 8565000 |  | 8565000
1.1 | Supply of Khandolite stone |  |  |  | 70% |  | 5995500
1.2 | Sizing work for required shape |  |  |  | 15% |  | 1284750
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 1284750
C | Steel Structure | 632 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Structural steel |  |  |  | 45% |  | 2569500
1.1.1 | Structural steel Assemblying and Erection |  |  |  | 25% |  | 1427500
1.2 | Supply of NFC wood |  |  |  | 30% |  | 1713000
D | Roofing & Finishing | 632 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Multiwall Polycarbonate sheet. |  |  |  | 60% |  | 3426000
1.1.1 | Laying and Fixing charge |  |  |  | 25% |  | 1427500
1.2 | Finishing |  |  |  | 15% |  | 856500
2.9 | External Services
A | External water supply |  |  | 1.5% |  | 17130000 |  | 17130000
1.1 | Supply of Materials |  |  |  | 70% |  | 11991000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 3426000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 1713000
B | External sewerage works |  |  | 0.25% |  | 2855000 |  | 2855000
1.1 | Supply of Materials |  |  |  | 70% |  | 1998500
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 571000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 285500
C | Rain water harvesting |  |  | 0.8% |  | 9136000 |  | 9136000
1.1 | Excavation and Boring |  |  |  | 15% |  | 1370400
1.2 | Brick work |  |  |  | 40% |  | 3654400
1.3 | Shuttering |  |  |  | 10% |  | 913600
1.4 | Supply of Reinforcement |  |  |  | 15% |  | 1370400
1.5 | Concrete |  |  |  | 10% |  | 913600
1.6 | Plastering |  |  |  | 10% |  | 913600
D | Landscaping & Horticulture |  |  | 1.1% |  | 12562000 |  | 12562000
1.1 | Supply of Materials |  |  |  | 70% |  | 8793400
1.2 | Laying and Fixing |  |  |  | 30% |  | 3768600
E | 1 year maintainance of Landscaping & Horticulture |  |  | 0.2% |  | 2284000 | 2284000 | 2284000
F | STP |  |  | 0.75% |  | 8565000 |  | 8565000
1.1 | Excavation |  |  |  | 5% |  | 428250
1.2 | Shuttering |  |  |  | 25% |  | 2141250
1.3 | Supply of Reinforcement |  |  |  | 40% |  | 3426000
1.4 | Concrete |  |  |  | 30% |  | 2569500
G | Garbage disposal/MCP |  |  | 0.2% |  | 2284000 |  | 2284000
1.1 | Supply of Materials |  |  |  | 85% |  | 1941400
1.2 | Handovering to uses |  |  |  | 15% |  | 342600
3 | External Illumination
i | On Completion Cable laying |  |  | 1% |  | 11420000 |  | 11420000
1.1 | Supply of Materials |  |  |  | 70% |  | 7994000
1.2 | Laying and Fixing of Materials |  |  |  | 30% |  | 3426000
ii | On Completion Erection of pole and light fittings |  |  | 6.8% |  | 77656000 |  | 77656000
1.1 | Supply of Materials |  |  |  | 70% |  | 54359200
1.2 | Laying and Fixing of Materials |  |  |  | 30% |  | 23296800
iii | On Completion of testing, commissioning and charging |  |  | 2% |  | 22840000 | 22840000 | 22840000
I | Transformer and DG |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Materials |  |  |  | 70% |  | 3997000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 1142000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 571000
J | Solar |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Materials |  |  |  | 70% |  | 3997000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 1142000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 571000
K | Fire fighting |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Materials |  |  |  | 70% |  | 3997000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 1142000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 571000
L | IP Surviliance, PA & LA |  |  | 1% |  | 11420000 |  | 11420000
1.1 | Supply of Materials |  |  |  | 70% |  | 7994000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 2284000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 1142000
M | Lightening Arrester |  |  | 0.2% |  | 2284000 |  | 2284000
1.1 | Supply of Materials |  |  |  | 70% |  | 1598800
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 456800
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 228400
N | Signages |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Notification Materials |  |  |  | 50% |  | 2855000
1.1.1 | Laying and Fixing of Materials |  |  |  | 15% |  | 856500
1.2 | Supply of Khandolite stone |  |  |  | 25% |  | 1427500
1.2.1 | Sizing work for required shape |  |  |  | 5% |  | 285500
1.2.2 | Laying and Fixing charge |  |  |  | 5% |  | 285500
3 | ACCEPTANCE STAGE
3.1 | Final approval from competent authority viz. development authority and 3Star GRIHA rating, testing, commissioning with approval from authority like fire officer and completion of all items as per approval. |  |  | 2.5% |  | 28550000 | 28550000 | 28550000
3.2 | On submission of As-Built drawings and other documents as mentioned in Contract Data |  |  | 0.5% |  | 5710000 | 5710000 | 5710000
Grand Total = | [5 empty] | 1142000000 | 1142000000 | 1142000000

## Payment Sche. Breakup% (hidden)
URC CONSTRUCTION (P) LTD
DEVELOPMENT OF MAA SAMALESWARI TEMPLE, ODISHA
Payment Schedule on Stage wise Value and % = | [5 empty] | 1142000000
Sl.no | Description of Item In Stage wise | Area | Unit | Weightage in % to the Contract | Sub-Percentage weightage | Amount In the Contract | Sub-Total weightage in Percentage to the Contract Price | Amount In Item wise | Remarks
1 | DESIGN STAGE |  |  | 2% |  | 22840000
1.1 | On approval of Inception Report, detail survey and draft architectural drawing & QMP |  |  |  | 25% |  |  | 5710000
1.1.1 | On approval of Inception Report |  |  |  | 30% |  | 1713000
1.1.2 | Detail survey Report |  |  |  | 30% |  | 1713000
1.1.3 | Draft of Architectural Drawing |  |  |  | 30% |  | 1713000
1.1.4 | Supmisson of QMP |  |  |  | 10% |  | 571000
1.2 | On approval of Site development plan and architectural drawing |  |  |  | 25% |  |  | 5710000
1.2.1 | Site development plan |  |  |  | 50% |  | 2855000
1.2.2 | Final architectural drawings |  |  |  | 50% |  | 2855000
1.3 | On approval of MEP |  |  |  | 25% |  |  | 5710000
1.3.1 | On approval of Design basis report showing electrical, sanitary, Fire Fighting |  |  |  | 30% |  | 1713000
1.3.2 | On approval of Electrical drawings |  |  |  | 30% |  | 1713000
1.3.3 | On Approval of PHE drawings |  |  |  | 20% |  | 1142000
1.3.4 | On approval of Firefighting drawings |  |  |  | 20% |  | 1142000
1.4 | On approval of final Architectural drawing showing electrical and sanitary layout plan and detail structural design and interior design/decoration |  |  |  | 25% |  |  | 5710000
1.4.1 | On approval of final Architectural drawing showing electrical and sanitary layout plan |  |  |  | 60% |  | 3426000
1.4.2 | On approval of final structural design and interior design/decoration |  |  |  | 40% |  | 2284000
2 | CONSTRUCTION STAGE
2.1 | Religious Facilities, Pilgrim Facilities, Information Counter, Vending Zone, Shoe Store, Crematorium, Clock Tower.
A | On Completion up to Plinth |  |  | 3% |  | 34260000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 2792376.5566
1.1 | Excavation |  |  |  | 5% |  | 139618.8278
1.2 | ATT |  |  |  | 2% |  | 55847.5311
1.3 | PCC |  |  |  | 10% |  | 279237.6557
1.4 | Footings - 102 nos |  |  |  | 30%
1.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 293199.5384
1.4.2 | Shuttering |  |  |  | 6% |  | 167542.5934
1.4.3 | Concrete |  |  |  | 13.5% |  | 376970.8351
1.5 | Column - 102 nos |  |  |  | 25%
1.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 314142.3626
1.5.2 | Shuttering |  |  |  | 6.25% |  | 174523.5348
1.5.3 | Concrete |  |  |  | 7.5% |  | 209428.2417
1.6 | Backfilling |  |  |  | 3% |  | 83771.2967
1.7 | Plinth beam |  |  |  | 25%
1.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 349047.0696
1.7.2 | Shuttering |  |  |  | 5% |  | 139618.8278
1.7.3 | Concrete |  |  |  | 7.5% |  | 209428.2417
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 7355616.3296
2.1 | Excavation |  |  |  | 5% |  | 367780.8165
2.2 | ATT |  |  |  | 2% |  | 147112.3266
2.3 | PCC |  |  |  | 10% |  | 735561.633
2.4 | Footings - 272 nos |  |  |  | 30%
2.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 772339.7146
2.4.2 | Shuttering |  |  |  | 6% |  | 441336.9798
2.4.3 | Concrete |  |  |  | 13.5% |  | 993008.2045
2.5 | Column - 272 nos |  |  |  | 25%
2.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 827506.8371
2.5.2 | Shuttering |  |  |  | 6.25% |  | 459726.0206
2.5.3 | Concrete |  |  |  | 7.5% |  | 551671.2247
2.6 | Backfilling |  |  |  | 3% |  | 220668.4899
2.7 | Plinth beam |  |  |  | 25%
2.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 919452.0412
2.7.2 | Shuttering |  |  |  | 5% |  | 367780.8165
2.7.3 | Concrete |  |  |  | 7.5% |  | 551671.2247
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 1103426.9723
3.1 | Excavation |  |  |  | 5% |  | 55171.3486
3.2 | ATT |  |  |  | 2% |  | 22068.5394
3.3 | PCC |  |  |  | 10% |  | 110342.6972
3.4 | Footings - 42 nos |  |  |  | 30%
3.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 115859.8321
3.4.2 | Shuttering |  |  |  | 6% |  | 66205.6183
3.4.3 | Concrete |  |  |  | 13.5% |  | 148962.6413
3.5 | Column - 42 nos |  |  |  | 25%
3.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 124135.5344
3.5.2 | Shuttering |  |  |  | 6.25% |  | 68964.1858
3.5.3 | Concrete |  |  |  | 7.5% |  | 82757.0229
3.6 | Backfilling |  |  |  | 3% |  | 33102.8092
3.7 | Plinth beam |  |  |  | 25%
3.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 137928.3715
3.7.2 | Shuttering |  |  |  | 5% |  | 55171.3486
3.7.3 | Concrete |  |  |  | 7.5% |  | 82757.0229
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 12325631.336
4.1 | Excavation |  |  |  | 5% |  | 616281.5668
4.2 | ATT |  |  |  | 2% |  | 246512.6267
4.3 | PCC |  |  |  | 10% |  | 1232563.1336
4.4 | Footings - 223 nos |  |  |  | 30%
4.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 1294191.2903
4.4.2 | Shuttering |  |  |  | 6% |  | 739537.8802
4.4.3 | Concrete |  |  |  | 13.5% |  | 1663960.2304
4.5 | Column - 223 nos |  |  |  | 25%
4.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 1386633.5253
4.5.2 | Shuttering |  |  |  | 6.25% |  | 770351.9585
4.5.3 | Concrete |  |  |  | 7.5% |  | 924422.3502
4.6 | Backfilling |  |  |  | 3% |  | 369768.9401
4.7 | Plinth beam |  |  |  | 25%
4.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 1540703.917
4.7.2 | Shuttering |  |  |  | 5% |  | 616281.5668
4.7.3 | Concrete |  |  |  | 7.5% |  | 924422.3502
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 1367064.6562
5.1 | Excavation |  |  |  | 5% |  | 68353.2328
5.2 | ATT |  |  |  | 2% |  | 27341.2931
5.3 | PCC |  |  |  | 10% |  | 136706.4656
5.4 | Footings - 09 nos |  |  |  | 30%
5.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 143541.7889
5.4.2 | Shuttering |  |  |  | 6% |  | 82023.8794
5.4.3 | Concrete |  |  |  | 13.5% |  | 184553.7286
5.5 | Column - 09 nos |  |  |  | 25%
5.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 153794.7738
5.5.2 | Shuttering |  |  |  | 6.25% |  | 85441.541
5.5.3 | Concrete |  |  |  | 7.5% |  | 102529.8492
5.6 | Backfilling |  |  |  | 3% |  | 41011.9397
5.7 | Plinth beam |  |  |  | 25%
5.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 170883.082
5.7.2 | Shuttering |  |  |  | 5% |  | 68353.2328
5.7.3 | Concrete |  |  |  | 7.5% |  | 102529.8492
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 5041969.6461
6.1 | Excavation |  |  |  | 5% |  | 252098.4823
6.2 | ATT |  |  |  | 2% |  | 100839.3929
6.3 | PCC |  |  |  | 10% |  | 504196.9646
6.4 | Footings - 152 nos |  |  |  | 30%
6.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 529406.8128
6.4.2 | Shuttering |  |  |  | 6% |  | 302518.1788
6.4.3 | Concrete |  |  |  | 13.5% |  | 680665.9022
6.5 | Column - 152 nos |  |  |  | 25%
6.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 567221.5852
6.5.2 | Shuttering |  |  |  | 6.25% |  | 315123.1029
6.5.3 | Concrete |  |  |  | 7.5% |  | 378147.7235
6.6 | Backfilling |  |  |  | 3% |  | 151259.0894
6.7 | Plinth beam |  |  |  | 25%
6.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 630246.2058
6.7.2 | Shuttering |  |  |  | 5% |  | 252098.4823
6.7.3 | Concrete |  |  |  | 7.5% |  | 378147.7235
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 4273914.5032
7.1 | Excavation |  |  |  | 5% |  | 213695.7252
7.2 | ATT |  |  |  | 2% |  | 85478.2901
7.3 | PCC |  |  |  | 10% |  | 427391.4503
7.4 | Footings - 148 nos |  |  |  | 30%
7.4.1 | Supply of Reinforcement |  |  |  | 10.5% |  | 448761.0228
7.4.2 | Shuttering |  |  |  | 6% |  | 256434.8702
7.4.3 | Concrete |  |  |  | 13.5% |  | 576978.4579
7.5 | Column - 148 nos |  |  |  | 25%
7.5.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 480815.3816
7.5.2 | Shuttering |  |  |  | 6.25% |  | 267119.6565
7.5.3 | Concrete |  |  |  | 7.5% |  | 320543.5877
7.6 | Backfilling |  |  |  | 3% |  | 128217.4351
7.7 | Plinth beam |  |  |  | 25%
7.7.1 | Supply of Reinforcement |  |  |  | 12.5% |  | 534239.3129
7.7.2 | Shuttering |  |  |  | 5% |  | 213695.7252
7.7.3 | Concrete |  |  |  | 7.5% |  | 320543.5877
B | On Completion Civil Structural work [Superstructure] |  |  | 6% |  | 68520000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 5584753.1131
1.1 | Column - 102 nos |  |  |  | 25%
1.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 628284.7252
1.1.2 | Shuttering |  |  |  | 6.25% |  | 349047.0696
1.1.3 | Concrete |  |  |  | 7.5% |  | 418856.4835
1.2 | Roof Slab |  |  |  | 45%
1.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 954992.7823
1.2.2 | Shuttering |  |  |  | 13.5% |  | 753941.6703
1.2.3 | Concrete |  |  |  | 14.4% |  | 804204.4483
1.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 1675425.9339
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 14711232.6592
2.1 | Column - 272 nos |  |  |  | 25%
2.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 1655013.6742
2.1.2 | Shuttering |  |  |  | 6.25% |  | 919452.0412
2.1.3 | Concrete |  |  |  | 7.5% |  | 1103342.4494
2.2 | Roof Slab |  |  |  | 45%
2.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 2515620.7847
2.2.2 | Shuttering |  |  |  | 13.5% |  | 1986016.409
2.2.3 | Concrete |  |  |  | 14.4% |  | 2118417.5029
2.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 4413369.7978
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 2206853.9445
3.1 | Column - 42 nos |  |  |  | 25%
3.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 248271.0688
3.1.2 | Shuttering |  |  |  | 6.25% |  | 137928.3715
3.1.3 | Concrete |  |  |  | 7.5% |  | 165514.0458
3.2 | Roof Slab |  |  |  | 45%
3.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 377372.0245
3.2.2 | Shuttering |  |  |  | 13.5% |  | 297925.2825
3.2.3 | Concrete |  |  |  | 14.4% |  | 317786.968
3.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 662056.1834
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 24651262.672
4.1 | Column - 223 nos |  |  |  | 25%
4.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 2773267.0506
4.1.2 | Shuttering |  |  |  | 6.25% |  | 1540703.917
4.1.3 | Concrete |  |  |  | 7.5% |  | 1848844.7004
4.2 | Roof Slab |  |  |  | 45%
4.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 4215365.9169
4.2.2 | Shuttering |  |  |  | 13.5% |  | 3327920.4607
4.2.3 | Concrete |  |  |  | 14.4% |  | 3549781.8248
4.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 7395378.8016
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 2734129.3125
5.1 | Column - 09 nos |  |  |  | 27%
I] Ground Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
II] First Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
III] Second Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
IV] Third Floor
5.1.1 | Supply of Reinforcement |  |  |  | 2.25% |  | 61517.9095
5.1.2 | Shuttering |  |  |  | 1% |  | 27341.2931
5.1.3 | Concrete |  |  |  | 1.5% |  | 41011.9397
V] Fourth Floor
5.1.1 | Supply of Reinforcement |  |  |  | 3.5% |  | 95694.5259
5.1.2 | Shuttering |  |  |  | 1.75% |  | 47847.263
5.1.3 | Concrete |  |  |  | 2.75% |  | 75188.5561
5.2 | Roof Slab/ Staircase |  |  |  | 48%
I] Ground Floor
5.2.1 | Supply of Reinforcement |  |  |  | 2% |  | 54682.5862
5.2.2 | Shuttering |  |  |  | 1.5% |  | 41011.9397
5.2.3 | Concrete |  |  |  | 2.5% |  | 68353.2328
II] First Floor
5.2.1 | Supply of Reinforcement |  |  |  | 2% |  | 54682.5862
5.2.2 | Shuttering |  |  |  | 1.5% |  | 41011.9397
5.2.3 | Concrete |  |  |  | 2.5% |  | 68353.2328
III] Second Floor
5.2.1 | Supply of Reinforcement |  |  |  | 2% |  | 54682.5862
5.2.2 | Shuttering |  |  |  | 1.5% |  | 41011.9397
5.2.3 | Concrete |  |  |  | 2.5% |  | 68353.2328
IV] Third Floor
5.2.1 | Supply of Reinforcement |  |  |  | 3.5% |  | 95694.5259
5.2.2 | Shuttering |  |  |  | 2.75% |  | 75188.5561
5.2.3 | Concrete |  |  |  | 4.5% |  | 123035.8191
V] Fourth Floor
5.2.1 | Supply of Reinforcement |  |  |  | 6.25% |  | 170883.082
5.2.2 | Shuttering |  |  |  | 5.5% |  | 150377.1122
5.2.3 | Concrete |  |  |  | 7.5% |  | 205059.6984
5.3 | Brick work with Ornamental/ Decorative |  |  |  | 25%
| I] Ground Floor |  |  |  | 8.5% |  | 232400.9916
| II] First Floor |  |  |  | 3.5% |  | 95694.5259
| III] Second Floor |  |  |  | 3.5% |  | 95694.5259
| IV] Third Floor |  |  |  | 3.5% |  | 95694.5259
| V] Fourth Floor |  |  |  | 6% |  | 164047.7587
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 10083939.2922
6.1 | Column - 152 nos |  |  |  | 25%
6.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 1134443.1704
6.1.2 | Shuttering |  |  |  | 6.25% |  | 630246.2058
6.1.3 | Concrete |  |  |  | 7.5% |  | 756295.4469
6.2 | Roof Slab |  |  |  | 45%
6.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 1724353.619
6.2.2 | Shuttering |  |  |  | 13.5% |  | 1361331.8044
6.2.3 | Concrete |  |  |  | 14.4% |  | 1452087.2581
6.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 3025181.7877
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 8547829.0064
7.1 | Column - 148 nos |  |  |  | 25%
7.1.1 | Supply of Reinforcement |  |  |  | 11.25% |  | 961630.7632
7.1.2 | Shuttering |  |  |  | 6.25% |  | 534239.3129
7.1.3 | Concrete |  |  |  | 7.5% |  | 641087.1755
7.2 | Roof Slab |  |  |  | 45%
7.2.1 | Supply of Reinforcement |  |  |  | 17.1% |  | 1461678.7601
7.2.2 | Shuttering |  |  |  | 13.5% |  | 1153956.9159
7.2.3 | Concrete |  |  |  | 14.4% |  | 1230887.3769
7.3 | Brick work with Ornamental/ Decorative |  |  |  | 30% |  | 2564348.7019
C | On Completion Khandolite masonry |  |  | 7% |  | 79940000
1 | Information counter | 127.89 | Cum |  | 14.35% |  |  | 11468038.094
1.1 | Supply of Khandolite stone |  |  |  | 70% |  | 8027626.6658
1.2 | Sizing work for required shape |  |  |  | 15% |  | 1720205.7141
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 1720205.7141
2 | Vending zone | 312.92 | Cum |  | 35.1% |  |  | 28059883.3401
2.1 | Supply of Khandolite stone |  |  |  | 70% |  | 19641918.338
2.2 | Sizing work for required shape |  |  |  | 15% |  | 4208982.501
2.3 | Laying and Fixing charge |  |  |  | 15% |  | 4208982.501
3 | Shoe store | 50.32 | Cum |  | 5.645% |  |  | 4512250.1907
3.1 | Supply of Khandolite stone |  |  |  | 70% |  | 3158575.1335
3.2 | Sizing work for required shape |  |  |  | 15% |  | 676837.5286
3.3 | Laying and Fixing charge |  |  |  | 15% |  | 676837.5286
4 | Clock tower | 14.26 | Cum |  | 1.6% |  |  | 1278710.0103
4.1 | Supply of Khandolite stone |  |  |  | 70% |  | 895097.0072
4.2 | Sizing work for required shape |  |  |  | 15% |  | 191806.5015
4.3 | Laying and Fixing charge |  |  |  | 15% |  | 191806.5015
5 | Religious Facilities | 201.78 | Cum |  | 22.63% |  |  | 18093836.3171
5.1 | Supply of Khandolite stone |  |  |  | 70% |  | 12665685.422
5.2 | Sizing work for required shape |  |  |  | 15% |  | 2714075.4476
5.3 | Laying and Fixing charge |  |  |  | 15% |  | 2714075.4476
6 | Pilgrim Facility | 184.31 | Cum |  | 20.67% |  |  | 16527282.0478
5.1 | Supply of Khandolite stone |  |  |  | 70% |  | 11569097.4335
5.2 | Sizing work for required shape |  |  |  | 15% |  | 2479092.3072
5.3 | Laying and Fixing charge |  |  |  | 15% |  | 2479092.3072
D | On completion of finishing work such as flooring, plastering, painting and other finishing works |  |  | 4% |  | 45680000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 3723168.7421
1.1 | Joineries work |  |  |  | 15%
1.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Roofing Shingles& Wood items |  |  |  | 10.5% |  | 390932.7179
1.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 167542.5934
1.2 | Plastering |  |  |  | 50%
1.2.1 | Ceiling |  |  |  | 12.5% |  | 465396.0928
1.2.2 | Internal |  |  |  | 20% |  | 744633.7484
1.2.3 | External |  |  |  | 17.5% |  | 651554.5299
1.3 | Flooring |  |  |  | 25%
1.3.1 | Supply of materials |  |  |  | 17.5% |  | 651554.5299
1.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 279237.6557
1.4 | Painting |  |  |  | 10%
1.4.1 | Ceiling |  |  |  | 2.5% |  | 93079.2186
1.4.2 | Internal |  |  |  | 4% |  | 148926.7497
1.4.3 | External |  |  |  | 3.5% |  | 130310.906
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 9807488.4395
2.1 | Joineries work |  |  |  | 15%
2.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Roofing Shingles& Wood items |  |  |  | 10.5% |  | 1029786.2861
2.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 441336.9798
2.2 | Plastering |  |  |  | 50%
2.2.1 | Ceiling |  |  |  | 12.5% |  | 1225936.0549
2.2.2 | Internal |  |  |  | 20% |  | 1961497.6879
2.2.3 | External |  |  |  | 17.5% |  | 1716310.4769
2.3 | Flooring |  |  |  | 25%
2.3.1 | Supply of materials |  |  |  | 17.5% |  | 1716310.4769
2.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 735561.633
2.4 | Painting |  |  |  | 10%
2.4.1 | Ceiling |  |  |  | 2.5% |  | 245187.211
2.4.2 | Internal |  |  |  | 4% |  | 392299.5376
2.4.3 | External |  |  |  | 3.5% |  | 343262.0954
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 1471235.963
3.1 | Joineries work |  |  |  | 15%
3.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 154479.7761
3.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 66205.6183
3.2 | Plastering |  |  |  | 50%
3.2.1 | Ceiling |  |  |  | 12.5% |  | 183904.4954
3.2.2 | Internal |  |  |  | 20% |  | 294247.1926
3.2.3 | External |  |  |  | 17.5% |  | 257466.2935
3.3 | Flooring |  |  |  | 25%
3.3.1 | Supply of materials |  |  |  | 17.5% |  | 257466.2935
3.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 110342.6972
3.4 | Painting |  |  |  | 10%
3.4.1 | Ceiling |  |  |  | 2.5% |  | 36780.8991
3.4.2 | Internal |  |  |  | 4% |  | 58849.4385
3.4.3 | External |  |  |  | 3.5% |  | 51493.2587
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 16434175.1147
4.1 | Joineries work |  |  |  | 15%
4.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 1725588.387
4.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 739537.8802
4.2 | Plastering |  |  |  | 50%
4.2.1 | Ceiling |  |  |  | 12.5% |  | 2054271.8893
4.2.2 | Internal |  |  |  | 20% |  | 3286835.0229
4.2.3 | External |  |  |  | 17.5% |  | 2875980.6451
4.3 | Flooring |  |  |  | 25%
4.3.1 | Supply of materials |  |  |  | 17.5% |  | 2875980.6451
4.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 1232563.1336
4.4 | Painting |  |  |  | 10%
4.4.1 | Ceiling |  |  |  | 2.5% |  | 410854.3779
4.4.2 | Internal |  |  |  | 4% |  | 657367.0046
4.4.3 | External |  |  |  | 3.5% |  | 575196.129
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 1822752.875
5.1 | Joineries work |  |  |  | 25%
I] Ground Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 5.5% |  | 100251.4081
5.1.2 | Fixing and Finishing |  |  |  | 1.5% |  | 27341.2931
II] First Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
III] Second Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
IV] Third Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
V] Fourth Floor
5.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works; Handrails & Wood items |  |  |  | 3.25% |  | 59239.4684
5.1.2 | Fixing and Finishing |  |  |  | 1.25% |  | 22784.4109
5.2 | Plastering |  |  |  | 40%
I] Ground Floor
5.2.1 | Ceiling |  |  |  | 1.5% |  | 27341.2931
5.2.2 | Internal |  |  |  | 2.5% |  | 45568.8219
5.2.3 | External |  |  |  | 2.5% |  | 45568.8219
II] First Floor
5.2.1 | Ceiling |  |  |  | 1.5% |  | 27341.2931
5.2.2 | Internal |  |  |  | 2.5% |  | 45568.8219
5.2.3 | External |  |  |  | 2.5% |  | 45568.8219
III] Second Floor
5.2.1 | Ceiling |  |  |  | 1.5% |  | 27341.2931
5.2.2 | Internal |  |  |  | 2.5% |  | 45568.8219
5.2.3 | External |  |  |  | 2.5% |  | 45568.8219
IV] Third Floor
5.2.1 | Ceiling |  |  |  | 2.5% |  | 45568.8219
5.2.2 | Internal |  |  |  | 2.75% |  | 50125.7041
5.2.3 | External |  |  |  | 2.75% |  | 50125.7041
V] Fourth Floor
5.2.1 | Ceiling |  |  |  | 3% |  | 54682.5862
5.2.2 | Internal |  |  |  | 5.25% |  | 95694.5259
5.2.3 | External |  |  |  | 4.25% |  | 77466.9972
5.3 | Flooring |  |  |  | 25%
I] Ground Floor
5.3.1 | Supply of materials |  |  |  | 5.25% |  | 95694.5259
5.3.2 | Laying and Leveling |  |  |  | 2% |  | 36455.0575
II] First Floor
5.3.1 | Supply of materials |  |  |  | 3% |  | 54682.5862
5.3.2 | Laying and Leveling |  |  |  | 1.25% |  | 22784.4109
III] Second Floor
5.3.1 | Supply of materials |  |  |  | 3% |  | 54682.5862
5.3.2 | Laying and Leveling |  |  |  | 1.25% |  | 22784.4109
IV] Third Floor
5.3.1 | Supply of materials |  |  |  | 3% |  | 54682.5862
5.3.2 | Laying and Leveling |  |  |  | 1.25% |  | 22784.4109
V] Fourth Floor
5.3.1 | Supply of materials |  |  |  | 3.5% |  | 63796.3506
5.3.2 | Laying and Leveling |  |  |  | 1.5% |  | 27341.2931
5.4 | Painting |  |  |  | 10%
I] Ground Floor
5.4.1 | Ceiling |  |  |  | 0.4% |  | 7291.0115
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
II] First Floor
5.4.1 | Ceiling |  |  |  | 0.4% |  | 7291.0115
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
III] Second Floor
5.4.1 | Ceiling |  |  |  | 0.4% |  | 7291.0115
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
IV] Third Floor
5.4.1 | Ceiling |  |  |  | 0.6% |  | 10936.5172
5.4.2 | Internal |  |  |  | 0.65% |  | 11847.8937
5.4.3 | External |  |  |  | 0.6% |  | 10936.5172
V] Fourth Floor
5.4.1 | Ceiling |  |  |  | 0.7% |  | 12759.2701
5.4.2 | Internal |  |  |  | 1.4% |  | 25518.5402
5.4.3 | External |  |  |  | 1.1% |  | 20050.2816
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 6722626.1948
6.1 | Joineries work |  |  |  | 15%
6.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 705875.7505
6.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 302518.1788
6.2 | Plastering |  |  |  | 50%
6.2.1 | Ceiling |  |  |  | 12.5% |  | 840328.2743
6.2.2 | Internal |  |  |  | 20% |  | 1344525.239
6.2.3 | External |  |  |  | 17.5% |  | 1176459.5841
6.3 | Flooring |  |  |  | 25%
6.3.1 | Supply of materials |  |  |  | 17.5% |  | 1176459.5841
6.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 504196.9646
6.4 | Painting |  |  |  | 10%
6.4.1 | Ceiling |  |  |  | 2.5% |  | 168065.6549
6.4.2 | Internal |  |  |  | 4% |  | 268905.0478
6.4.3 | External |  |  |  | 3.5% |  | 235291.9168
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 5698552.671
7.1 | Joineries work |  |  |  | 15%
7.1.1 | Supply of materials - MS Grill/Shutters; Aluminium works& Wood items |  |  |  | 10.5% |  | 598348.0305
7.1.2 | Fixing and Finishing |  |  |  | 4.5% |  | 256434.8702
7.2 | Plastering |  |  |  | 50%
7.2.1 | Ceiling |  |  |  | 12.5% |  | 712319.0839
7.2.2 | Internal |  |  |  | 20% |  | 1139710.5342
7.2.3 | External |  |  |  | 17.5% |  | 997246.7174
7.3 | Flooring |  |  |  | 25%
7.3.1 | Supply of materials |  |  |  | 17.5% |  | 997246.7174
7.3.2 | Laying and Leveling |  |  |  | 7.5% |  | 427391.4503
7.4 | Painting |  |  |  | 10%
7.4.1 | Ceiling |  |  |  | 2.5% |  | 142463.8168
7.4.2 | Internal |  |  |  | 4% |  | 227942.1068
7.4.3 | External |  |  |  | 3.5% |  | 199449.3435
E | Internal Water supply & Sanitary Installation |  |  | 1% |  | 11420000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 930792.1855
1.1 | Supply of Materials |  |  |  | 70% |  | 651554.5299
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 186158.4371
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 93079.2186
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 2451872.1099
2.1 | Supply of Materials |  |  |  | 70% |  | 1716310.4769
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 490374.422
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 245187.211
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 367808.9908
3.1 | Supply of Materials |  |  |  | 70% |  | 257466.2935
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 73561.7982
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 36780.8991
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 4108543.7787
4.1 | Supply of Materials |  |  |  | 70% |  | 2875980.6451
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 821708.7557
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 410854.3779
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 455688.2187
5.1 | Supply of Materials |  |  |  | 70% |  | 318981.7531
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 91137.6437
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 45568.8219
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 1680656.5487
6.1 | Supply of Materials |  |  |  | 70% |  | 1176459.5841
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 336131.3097
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 168065.6549
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 1424638.1677
7.1 | Supply of Materials |  |  |  | 70% |  | 997246.7174
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 284927.6335
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 142463.8168
F | External Water supply & Sanitary Installation |  |  | 0.5% |  | 5710000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 465396.0928
1.1 | Supply of Materials |  |  |  | 70% |  | 325777.2649
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 93079.2186
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 46539.6093
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 1225936.0549
2.1 | Supply of Materials |  |  |  | 70% |  | 858155.2385
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 245187.211
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 122593.6055
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 183904.4954
3.1 | Supply of Materials |  |  |  | 70% |  | 128733.1468
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 36780.8991
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 18390.4495
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 2054271.8893
4.1 | Supply of Materials |  |  |  | 70% |  | 1437990.3225
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 410854.3779
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 205427.1889
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 227844.1094
5.1 | Supply of Materials |  |  |  | 70% |  | 159490.8766
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 45568.8219
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 22784.4109
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 840328.2743
6.1 | Supply of Materials |  |  |  | 70% |  | 588229.792
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 168065.6549
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 84032.8274
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 712319.0839
7.1 | Supply of Materials |  |  |  | 70% |  | 498623.3587
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 142463.8168
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 71231.9084
G | Internal electric Installations |  |  | 1% |  | 11420000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 930792.1855
1.1 | Supply of Materials |  |  |  | 70% |  | 651554.5299
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 186158.4371
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 93079.2186
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 2451872.1099
2.1 | Supply of Materials |  |  |  | 70% |  | 1716310.4769
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 490374.422
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 245187.211
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 367808.9908
3.1 | Supply of Materials |  |  |  | 70% |  | 257466.2935
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 73561.7982
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 36780.8991
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 4108543.7787
4.1 | Supply of Materials |  |  |  | 70% |  | 2875980.6451
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 821708.7557
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 410854.3779
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 455688.2187
5.1 | Supply of Materials |  |  |  | 70% |  | 318981.7531
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 91137.6437
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 45568.8219
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 1680656.5487
6.1 | Supply of Materials |  |  |  | 70% |  | 1176459.5841
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 336131.3097
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 168065.6549
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 1424638.1677
7.1 | Supply of Materials |  |  |  | 70% |  | 997246.7174
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 284927.6335
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 142463.8168
H | External electric Installations |  |  | 0.5% |  | 5710000
1 | Information counter | 759.85 | Sqm |  | 8.151% |  |  | 465396.0928
1.1 | Supply of Materials |  |  |  | 70% |  | 325777.2649
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 93079.2186
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 46539.6093
2 | Vending zone | 2001.58 | Sqm |  | 21.47% |  |  | 1225936.0549
2.1 | Supply of Materials |  |  |  | 70% |  | 858155.2385
2.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 245187.211
2.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 122593.6055
3 | Shoe store | 300.26 | Sqm |  | 3.221% |  |  | 183904.4954
3.1 | Supply of Materials |  |  |  | 70% |  | 128733.1468
3.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 36780.8991
3.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 18390.4495
4 | Crematorium | 3354 | Sqm |  | 35.98% |  |  | 2054271.8893
4.1 | Supply of Materials |  |  |  | 70% |  | 1437990.3225
4.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 410854.3779
4.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 205427.1889
5 | Clock tower | 372 | Sqm |  | 3.99% |  |  | 227844.1094
5.1 | Supply of Materials |  |  |  | 70% |  | 159490.8766
5.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 45568.8219
5.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 22784.4109
6 | Religious Facilities | 1372 | Sqm |  | 14.72% |  |  | 840328.2743
6.1 | Supply of Materials |  |  |  | 70% |  | 588229.792
6.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 168065.6549
6.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 84032.8274
7 | Pilgrim Facility | 1163 | Sqm |  | 12.47% |  |  | 712319.0839
7.1 | Supply of Materials |  |  |  | 70% |  | 498623.3587
7.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 142463.8168
7.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 71231.9084
2.2 | Foot over Bridge & QMS
A | On Completion up to Plinth |  |  | 2% |  | 22840000
1 | Foot over Bridge | 666 | Sqm |  | 27.41% |  |  | 6259851.8519
1.1 | Excavation |  |  |  | 5% |  | 312992.5926
1.2 | Supply of Reinforcement |  |  |  | 50% |  | 3129925.9259
1.3 | Shuttering work |  |  |  | 15% |  | 938977.7778
1.4 | Concrete works |  |  |  | 25% |  | 1564962.963
1.5 | Backfilling |  |  |  | 5% |  | 312992.5926
2 | Que Management System | 1764 | Sqm |  | 72.59% |  |  | 16580148.1481
2.1 | Excavation |  |  |  | 5% |  | 829007.4074
2.2 | Supply of Reinforcement |  |  |  | 50% |  | 8290074.0741
2.3 | Shuttering work |  |  |  | 15% |  | 2487022.2222
2.4 | Concrete works |  |  |  | 25% |  | 4145037.037
2.5 | Backfilling |  |  |  | 5% |  | 829007.4074
B | On Completion Civil Structural work |  |  | 3% |  | 34260000
1 | Foot over Bridge | 666 | Sqm |  | 27.41% |  |  | 9389777.7778
1.1 | Supply of Reinforcement |  |  |  | 20% |  | 1877955.5556
1.2 | Shuttering |  |  |  | 10% |  | 938977.7778
1.3 | Concrete |  |  |  | 15% |  | 1408466.6667
1.4 | Supply of Structural steel |  |  |  | 40% |  | 3755911.1111
1.4.1 | Structural steel Assemblying and Erection |  |  |  | 15% |  | 1408466.6667
2 | Que Management System | 1764 | Sqm |  | 72.59% |  |  | 24870222.2222
2.1 | Supply of Reinforcement |  |  |  | 20% |  | 4974044.4444
2.2 | Shuttering |  |  |  | 10% |  | 2487022.2222
2.3 | Concrete |  |  |  | 15% |  | 3730533.3333
2.4 | Supply of Structural steel |  |  |  | 40% |  | 9948088.8889
2.4.1 | Structural steel Assemblying and Erection |  |  |  | 15% |  | 3730533.3333
C | On completion of finishing work such as roofing, flooring, plastering, painting, NFC cladding and other finishing works |  |  | 3% |  | 34260000
1 | Foot over Bridge | 666 | Sqm |  | 27.41% |  |  | 9389777.7778
1.1 | Supply of Granite |  |  |  | 43% |  | 4037604.4444
1.1.1 | Laying and Fixing |  |  |  | 17% |  | 1596262.2222
1.2 | Supply of 23mm Tks wood polymer composite |  |  |  | 28% |  | 2629137.7778
1.2.1 | Laying and Fixing |  |  |  | 12% |  | 1126773.3333
2 | Que Management System | 1764 | Sqm |  | 72.59% |  |  | 24870222.2222
2.1 | Supply of Khandolite stone |  |  |  | 25% |  | 6217555.5556
2.1.1 | Sizing work for required shape |  |  |  | 3% |  | 746106.6667
2.1.2 | Laying and Fixing |  |  |  | 2% |  | 497404.4444
2.2 | Supply of SS handrail |  |  |  | 20% |  | 4974044.4444
2.2.1 | Laying and Fixing |  |  |  | 5% |  | 1243511.1111
2.3 | Supply of Multi wall Polycarbonate sheet |  |  |  | 15% |  | 3730533.3333
2.3.1 | Laying and Fixing |  |  |  | 5% |  | 1243511.1111
2.4 | Supply of NFC wood material. |  |  |  | 15% |  | 3730533.3333
2.4.1 | Laying and Fixing |  |  |  | 5% |  | 1243511.1111
2.5 | Supply of Landscapping. |  |  |  | 3% |  | 746106.6667
2.5.1 | Laying work |  |  |  | 2% |  | 497404.4444
2.3 | Compound wall & Heritage Gate
A | On Completion up to Plinth |  |  | 0.5% |  | 5710000
1 | Compound wall | 910 | Mtr |  | 94.99% |  |  | 5423903.9666
1.1 | Excavation |  |  |  | 10% |  | 542390.3967
1.2 | Supply of Reinforcement |  |  |  | 40% |  | 2169561.5866
1.3 | Shuttering work |  |  |  | 20% |  | 1084780.7933
1.4 | Concrete works |  |  |  | 25% |  | 1355975.9916
1.5 | Backfilling |  |  |  | 5% |  | 271195.1983
2 | Heritage Gate | 48 | Mtr |  | 5.01% |  |  | 286096.0334
2.1 | Excavation |  |  |  | 10% |  | 28609.6033
2.2 | Supply of Reinforcement |  |  |  | 40% |  | 114438.4134
2.3 | Shuttering work |  |  |  | 20% |  | 57219.2067
2.4 | Concrete works |  |  |  | 25% |  | 71524.0084
2.5 | Backfilling |  |  |  | 5% |  | 14304.8017
B | On Completion Civil Structural work |  |  | 2% |  | 22840000
1 | Compound wall | 910 | Mtr |  | 94.99% |  |  | 21695615.8664
1.1 | Supply of Reinforcement |  |  |  | 25% |  | 5423903.9666
1.2 | Shuttering |  |  |  | 8% |  | 1735649.2693
1.3 | Concrete |  |  |  | 13% |  | 2820430.0626
1.4 | Brick work with Ornamental/ Decorative |  |  |  | 14% |  | 3037386.2213
1.5 | Supply of Structural steel - Grill |  |  |  | 40% |  | 8678246.3466
2 | Heritage Gate | 48 | Mtr |  | 5.01% |  |  | 1144384.1336
2.1 | Supply of Reinforcement |  |  |  | 15% |  | 171657.62
2.2 | Shuttering |  |  |  | 7% |  | 80106.8894
2.3 | Concrete |  |  |  | 9% |  | 102994.572
2.4 | Brick work with Ornamental/ Decorative |  |  |  | 14% |  | 160213.7787
2.5 | Supply of Structural steel - Gate |  |  |  | 55% |  | 629411.2735
C | On completion of finishing work such as carving, plastering, painting and other finishing works |  |  | 0.5% |  | 5710000
1 | Compound wall | 910 | Mtr |  | 94.99% |  |  | 5423903.9666
1.1 | Supply of Khandolite stone |  |  |  | 60% |  | 3254342.38
1.1.1 | Sizing work for required shape |  |  |  | 15% |  | 813585.595
1.1.2 | Laying and Fixing |  |  |  | 10% |  | 542390.3967
1.2 | Plastering |  |  |  | 10% |  | 542390.3967
1.3 | Painting |  |  |  | 5% |  | 271195.1983
2 | Heritage Gate | 48 | Mtr |  | 5.01% |  |  | 286096.0334
2.1 | Supply of Khandolite stone |  |  |  | 52% |  | 148769.9374
2.1.1 | Sizing work for required shape |  |  |  | 15% |  | 42914.405
2.1.2 | Laying and Fixing |  |  |  | 10% |  | 28609.6033
2.2 | Plastering |  |  |  | 15% |  | 42914.405
2.3 | Painting |  |  |  | 8% |  | 22887.6827
2.4 | River front development
A | On Completion of structural work upto formation ground level . |  |  | 5% |  | 57100000 |  | 57100000
1.1 | Excavation |  |  |  | 2.5% |  | 1427500
1.2 | Supply of Reinforcement |  |  |  | 40% |  | 22840000
1.3 | Shuttering work |  |  |  | 24% |  | 13704000
1.4 | Concrete works |  |  |  | 32% |  | 18272000
1.5 | Filling work |  |  |  | 1.5% |  | 856500
B | On Completion Civil Structural work |  |  | 5% |  | 57100000 |  | 57100000
1.1 | Supply of Reinforcement |  |  |  | 40% |  | 22840000
1.2 | Shuttering |  |  |  | 20% |  | 11420000
1.3 | Concrete |  |  |  | 40% |  | 22840000
C | On Completion Paving. |  |  | 5% |  | 57100000 |  | 57100000
1.1 | Supply of Materials |  |  |  | 70% |  | 39970000
1.2 | Laying and Fixing |  |  |  | 30% |  | 17130000
D | On completion of finishing work such as plastering, painting and other finishing works |  |  | 1% |  | 11420000 |  | 11420000
1.1 | Brick work |  |  |  | 45% |  | 5139000
1.2 | Plastering |  |  |  | 45% |  | 5139000
1.3 | Painting |  |  |  | 10% |  | 1142000
2.5 | Parking
A | On Completion Foundation plinth | 23000 | Sqm | 0.3% |  | 3426000 |  | 3426000
1.1 | Excavation |  |  |  | 15% |  | 513900
1.2 | Shuttering work |  |  |  | 25% |  | 856500
1.3 | Concrete works |  |  |  | 60% |  | 2055600
B | On Completion Subbase & Base | 23000 | Sqm | 1% |  | 11420000 |  | 11420000
1.1 | Excavation; Filling and Ramping work |  |  |  | 30% |  | 3426000
1.2 | Subbase work |  |  |  | 70% |  | 7994000
C | On Completion Paving . | 23000 | Sqm | 1.5% |  | 17130000 |  | 17130000
1.1 | Supply of Materials |  |  |  | 70% |  | 11991000
1.2 | Laying and Fixing |  |  |  | 30% |  | 5139000
D | On completion of finishing work such as plastering, painting and other finishing works | 23000 | Sqm | 0.2% |  | 2284000 |  | 2284000
1.1 | Brick work |  |  |  | 45% |  | 1027800
1.2 | Plastering |  |  |  | 40% |  | 913600
1.3 | Painting |  |  |  | 15% |  | 342600
2.6 | Pathway/Walkway
A | On Completion Foundation plinth . |  | Sqm | 1% |  | 11420000 |  | 11420000
1.1 | Excavation |  |  |  | 15% |  | 1713000
1.2 | Shuttering work |  |  |  | 25% |  | 2855000
1.3 | Concrete works |  |  |  | 60% |  | 6852000
B | On Completion Subbase & Base . |  | Sqm | 2% |  | 22840000 |  | 22840000
1.1 | Excavation; Filling and Ramping work |  |  |  | 30% |  | 6852000
1.2 | Subbase work |  |  |  | 70% |  | 15988000
C | On Completion Paving . |  | Sqm | 13% |  | 148460000 |  | 148460000
1.1 | Supply of Khandolite stone/Square granite cobbles |  |  |  | 70% |  | 103922000
1.2 | Sizing work for required shape |  |  |  | 15% |  | 22269000
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 22269000
D | On completion of finishing work such as plastering, painting and other finishing works |  | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Brick work |  |  |  | 40% |  | 2284000
1.2 | Plastering |  |  |  | 25% |  | 1427500
1.3 | Applying of Nitocote wall guard |  |  |  | 20% |  | 1142000
1.4 | Painting |  |  |  | 15% |  | 856500
2.7 | Heritage corridor
A | On Completion of drain . [900 Rmt] | 900 | Rmt | 1.2% |  | 13704000 |  | 13704000
1.1 | Excavation |  |  |  | 15% |  | 2055600
1.2 | Supply of Reinforcement |  |  |  | 10% |  | 1370400
1.3 | Shuttering work |  |  |  | 10% |  | 1370400
1.4 | Concrete works |  |  |  | 15% |  | 2055600
1.5 | Brick work |  |  |  | 50% |  | 6852000
B | On Completion Subbase & Base . | 18000 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Excavation; Filling and Ramping work |  |  |  | 30% |  | 1713000
1.2 | Subbase work |  |  |  | 70% |  | 3997000
C | On Completion Paving . | 18000 | Sqm | 3.5% |  | 39970000 |  | 39970000
1.1 | Supply of Natural Square granite cobbles |  |  |  | 70% |  | 27979000
1.2 | Sizing work for required shape |  |  |  | 15% |  | 5995500
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 5995500
D | On completion of finishing work such as plastering, painting and other finishing works | 18000 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Plastering |  |  |  | 90% |  | 5139000
1.2 | Painting |  |  |  | 10% |  | 571000
2.8 | Waterbody and Sitouts
A | On Completion Foundation and sub structure . | 632 | Sqm | 0.25% |  | 2855000 |  | 2855000
1.1 | Excavation |  |  |  | 15% |  | 428250
1.2 | Supply of Reinforcement |  |  |  | 40% |  | 1142000
1.3 | Shuttering work |  |  |  | 20% |  | 571000
1.4 | Concrete works |  |  |  | 25% |  | 713750
B | On Completion Paving/sitouts . | 632 | Sqm | 0.75% |  | 8565000 |  | 8565000
1.1 | Supply of Khandolite stone |  |  |  | 70% |  | 5995500
1.2 | Sizing work for required shape |  |  |  | 15% |  | 1284750
1.3 | Laying and Fixing charge |  |  |  | 15% |  | 1284750
C | Steel Structure | 632 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Structural steel |  |  |  | 45% |  | 2569500
1.1.1 | Structural steel Assemblying and Erection |  |  |  | 25% |  | 1427500
1.2 | Supply of NFC wood |  |  |  | 30% |  | 1713000
D | Roofing & Finishing | 632 | Sqm | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Multiwall Polycarbonate sheet. |  |  |  | 60% |  | 3426000
1.1.1 | Laying and Fixing charge |  |  |  | 25% |  | 1427500
1.2 | Finishing |  |  |  | 15% |  | 856500
2.9 | External Services
A | External water supply |  |  | 1.5% |  | 17130000 |  | 17130000
1.1 | Supply of Materials |  |  |  | 70% |  | 11991000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 3426000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 1713000
B | External sewerage works |  |  | 0.25% |  | 2855000 |  | 2855000
1.1 | Supply of Materials |  |  |  | 70% |  | 1998500
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 571000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 285500
C | Rain water harvesting |  |  | 0.8% |  | 9136000 |  | 9136000
1.1 | Excavation and Boring |  |  |  | 15% |  | 1370400
1.2 | Brick work |  |  |  | 40% |  | 3654400
1.3 | Shuttering |  |  |  | 10% |  | 913600
1.4 | Supply of Reinforcement |  |  |  | 15% |  | 1370400
1.5 | Concrete |  |  |  | 10% |  | 913600
1.6 | Plastering |  |  |  | 10% |  | 913600
D | Landscaping & Horticulture |  |  | 1.1% |  | 12562000 |  | 12562000
1.1 | Supply of Materials |  |  |  | 70% |  | 8793400
1.2 | Laying and Fixing |  |  |  | 30% |  | 3768600
E | 1 year maintainance of Landscaping & Horticulture |  |  | 0.2% |  | 2284000 | 2284000 | 2284000
F | STP |  |  | 0.75% |  | 8565000 |  | 8565000
1.1 | Excavation |  |  |  | 5% |  | 428250
1.2 | Shuttering |  |  |  | 25% |  | 2141250
1.3 | Supply of Reinforcement |  |  |  | 40% |  | 3426000
1.4 | Concrete |  |  |  | 30% |  | 2569500
G | Garbage disposal/MCP |  |  | 0.2% |  | 2284000 |  | 2284000
1.1 | Supply of Materials |  |  |  | 85% |  | 1941400
1.2 | Handovering to uses |  |  |  | 15% |  | 342600
3 | External Illumination
i | On Completion Cable laying |  |  | 1% |  | 11420000 |  | 11420000
1.1 | Supply of Materials |  |  |  | 70% |  | 7994000
1.2 | Laying and Fixing of Materials |  |  |  | 30% |  | 3426000
ii | On Completion Erection of pole and light fittings |  |  | 6.8% |  | 77656000 |  | 77656000
1.1 | Supply of Materials |  |  |  | 70% |  | 54359200
1.2 | Laying and Fixing of Materials |  |  |  | 30% |  | 23296800
iii | On Completion of testing, commissioning and charging |  |  | 2% |  | 22840000 | 22840000 | 22840000
I | Transformer and DG |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Materials |  |  |  | 70% |  | 3997000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 1142000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 571000
J | Solar |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Materials |  |  |  | 70% |  | 3997000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 1142000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 571000
K | Fire fighting |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Materials |  |  |  | 70% |  | 3997000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 1142000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 571000
L | IP Surviliance, PA & LA |  |  | 1% |  | 11420000 |  | 11420000
1.1 | Supply of Materials |  |  |  | 70% |  | 7994000
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 2284000
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 1142000
M | Lightening Arrester |  |  | 0.2% |  | 2284000 |  | 2284000
1.1 | Supply of Materials |  |  |  | 70% |  | 1598800
1.2 | Laying and Fixing of Materials |  |  |  | 20% |  | 456800
1.3 | Charge for Testing and Commissioning |  |  |  | 10% |  | 228400
N | Signages |  |  | 0.5% |  | 5710000 |  | 5710000
1.1 | Supply of Notification Materials |  |  |  | 50% |  | 2855000
1.1.1 | Laying and Fixing of Materials |  |  |  | 15% |  | 856500
1.2 | Supply of Khandolite stone |  |  |  | 25% |  | 1427500
1.2.1 | Sizing work for required shape |  |  |  | 5% |  | 285500
1.2.2 | Laying and Fixing charge |  |  |  | 5% |  | 285500
3 | ACCEPTANCE STAGE
3.1 | Final approval from competent authority viz. development authority and 3Star GRIHA rating, testing, commissioning with approval from authority like fire officer and completion of all items as per approval. |  |  | 2.5% |  | 28550000 | 28550000 | 28550000
3.2 | On submission of As-Built drawings and other documents as mentioned in Contract Data |  |  | 0.5% |  | 5710000 | 5710000 | 5710000
Grand Total = | [5 empty] | 1142000000 | 1142000000 | 1142000000

## Payment Schedule-RFI (hidden)
PAYMENT SCHEDULE OF SAMALEI PROJECT |  |  |  | CONTRACT VALUE
SL NO |  | ACTIVITY | PAYMENT AS % OF AGREEMENT COST | 1142000000
1 |  | DESIGN STAGE
| 1.1 | On approval of Inception Report, detail survey and draft architectural drawing & QMP | 0.5% | 5710000
| 1.2 | On approval of Site development plan and architectural drawing | 0.5% | 5710000
| 1.3 | On approval of MEP | 0.5% | 5710000
| 1.4 | On approval of final Architectural drawing showing electrical and sanitary layout plan and detail structural design and interior design/decoration | 0.5% | 5710000
|  | TOTAL - Design Stage | 2% | 22840000
2 |  | CONSTRUCTION STAGE
| 2.1 | Religious Facilities, Pilgrim Facilities, Information Counter, Vending Zone, Shoe Store, Crematorium, Clock Tower etc
| a | On Completion up to Plinth | 3% | 34260000
| b | On Completion Civil Structural work | 6% | 68520000
| c | On Completion Khandolite masonry | 7% | 79940000
| d | On completion of finishing work such as flooring, plastering, painting and other finishing works | 4% | 45680000
| e | Internal Water supply & Sanitary Installation | 1% | 11420000
| f | External Water supply & Sanitary Installation | 0.5% | 5710000
| g | Internal electric Installations | 1% | 11420000
| h | External electric Installations | 0.5% | 5710000
| 2.2 | Foot over Bridge & QMS | 0% | 0
| a | On Completion up to Plinth | 2% | 22840000
| b | On Completion Civil Structural work | 3% | 34260000
| c | On completion of finishing work such as roofing, flooring, plastering, painting, NFC cladding and other finishing works | 3% | 34260000
| 2.3 | Compound wall & Heritage Gate |  | 0
| a | On Completion up to Plinth | 0.5% | 5710000
| b | On Completion Civil Structural work | 2% | 22840000
| c | On completion of finishing work such as carving, plastering, painting and other finishing works | 0.5% | 5710000
| 2.4 | River front development | 0% | 0
| a | On Completion of structural work upto formation ground level . | 5% | 57100000
| b | On Completion Civil Structural work | 5% | 57100000
| c | On Completion Paving. | 5% | 57100000
| d | On completion of finishing work such as plastering, painting and other finishing works | 1% | 11420000
| 2.5 | Parking | 0% | 0
| a | On Completion Foundation plinth | 0.3% | 3426000
| b | On Completion Subbase & Base | 1% | 11420000
| c | On Completion Paving . | 1.5% | 17130000
| d | On completion of finishing work such as plastering, painting and other finishing works | 0.2% | 2284000
| 2.6 | Pathway/Walkway | 0% | 0
| a | On Completion Foundation plinth . | 1% | 11420000
| b | On Completion Subbase & Base . | 2% | 22840000
| c | On Completion Paving . | 13% | 148460000
| d | On completion of finishing work such as plastering, painting and other finishing works | 0.5% | 5710000
| 2.7 | Heritage corridor | 0% | 0
| a | On Completion of drain . | 1.2% | 13704000
| b | On Completion Subbase & Base . | 0.5% | 5710000
| c | On Completion Paving . | 3.5% | 39970000
| d | On completion of finishing work such as plastering, painting and other finishing works | 0.5% | 5710000
| 2.8 | Waterbody and Sitouts | 0% | 0
| a | On Completion Foundation and sub structure . | 0.25% | 2855000
| b | On Completion Paving/sitouts . | 0.75% | 8565000
| c | Steel Structure | 0.5% | 5710000
| d | Roofing & Finishing | 0.5% | 5710000
| 2.9 | External Services | 0% | 0
| a | External water supply | 1.5% | 17130000
| b | External sewerage works | 0.25% | 2855000
| c | Rain water harvesting | 0.8% | 9136000
| d | Landscaping & Horticulture | 1.1% | 12562000
| e | 1 year maintainance of Landscaping & Horticulture | 0.2% | 2284000
| f | STP | 0.75% | 8565000
| g | Garbage disposal/MCP | 0.2% | 2284000
| h | External Illumination | 0% | 0
| i | On Completion Cable laying | 1% | 11420000
| ii | On Completion Erection of pole and light fittings | 6.8% | 77656000
| iii | On Completion of testing, commissioning and charging | 2% | 22840000
| i | Transformer and DG | 0.5% | 5710000
| j | Solar | 0.5% | 5710000
| k | Fire fighting | 0.5% | 5710000
| l | IP Surviliance, PA & LA | 1% | 11420000
| m | Lightening Arrester | 0.2% | 2284000
| n | Signages | 0.5% | 5710000
|  | TOTAL - Construction Stage | 95% | 1084900000
3 |  | ACCEPTANCE STAGE
| 3.1 | Final approval from competent authority viz. development authority and 3Star GRIHA rating, testing, commissioning with approval from authority like fire officer and completion of all items as per approval. | 2.5% | 28550000
| 3.2 | On submission of As-Built drawings and other documents as mentioned in Contract Data | 0.5% | 5710000
|  | TOTAL - Acceptance Stage | 3% | 34260000
|  | GRAND TOTAL | 100% | 1142000000

## Sec. 4 Dedu Interest (hidden)
CLIENT : ODISHA BRIDGE & CONSTRUCTION CORPORATION LIMITED
CONTRACTOR : URC CONSTRUCTION (P) LTD
PROJECT NAME : Design & Construction of Maa Samaleswari Temple Area Under Samalei Plan on Lumpsum Turnkey Basis
Details of Mobilisation advance Interest Deductions
Sl no | Description | Mob Amount | Mob Recovery Amount | Interest Period |  |  | Interest Paid Amount | Remarks
|  |  |  | From Date | To date | No of days
1 | RAB 01 | 114200000 | #REF! | 2022-08-08 | 2022-08-31 | 24 | #REF!
2 | RAB 02 | #REF! |  |  |  |  | #REF!
3 | RAB 03 | #REF! |  |  |  |  | #REF!
4 | RAB 04 | #REF! |  |  |  |  | #REF!
5 | RAB 05 | #REF! |  |  |  |  | #REF!
6 | RAB 06 | #REF! |  |  |  |  | #REF!
7 | RAB 07 | #REF! |  |  |  |  | #REF!
8 | RAB 08 | #REF! |  |  |  |  | #REF!
9 | RAB 09 | #REF! |  |  |  |  | #REF!
10 | RAB 10 | #REF! |  |  |  |  | #REF!
11 | RAB 11 | #REF! |  |  |  |  | #REF!
12 | RAB 12 | #REF! |  |  |  |  | #REF!
13 | RAB 13 | #REF! |  |  |  |  | #REF!
14 | RAB 14 | #REF! |  |  |  |  | #REF!
15 | RAB 15 | #REF! |  |  |  |  | #REF!
16 | RAB 16 | #REF! |  |  |  |  | #REF!
17 | RAB 17 | #REF! |  |  |  |  | #REF!
18 | RAB 18 | #REF! |  |  |  |  | #REF!
Total Amount | [6 empty] | #REF!

## WCP- VZ (hidden)
URC Construction (P) Ltd
Odisha Bridge & Construction Corporation Limited
Development of Maa Samaleswari Temple Area
Name of The Building : Vending Zone |  |  | Work Completed Percentage Details
Sl. no | Description of Items | Unit | Completed Items |  |  | % For Completed Items |  |  | Remarks
|  |  | Upto Previous Bill | Current Bill | Cumulative Bill | Upto Previous Bill | Current Bill | Cumulative Bill
2 | CONSTRUCTION STAGE
A | On Completion up to Plinth
2.1 | Excavation | Ls |  | 0.9 | 0.9 |  | 90% | 90%
2.2 | ATT | Ls |  | 0.62868 | 0.62868 |  | 62.87% | 62.87%
2.3 | PCC | Ls |  | 0.62868 | 0.62868 |  | 62.87% | 62.87%
2.4 | Footings - 272 nos |  |  |  | 0 |  |  | 0%
2.4.1 | Supply of Reinforcement | Nos |  | 272 | 272 |  | 100% | 100%
2.4.2 | Shuttering | Nos |  | 150 | 150 |  | 55.15% | 55.15%
2.4.3 | Concrete | Nos |  | 150 | 150 |  | 55.15% | 55.15%
2.5 | Column - 272 nos |  |  |  | 0 |  |  | 0%
2.5.1 | Supply of Reinforcement | Nos |  | 272 | 272 |  | 100% | 100%
2.5.2 | Shuttering | Nos |  | 120 | 120 |  | 44.12% | 44.12%
2.5.3 | Concrete | Nos |  | 120 | 120 |  | 44.12% | 44.12%
2.6 | Backfilling | Ls |  |  | 0 |  |  | 0%
2.7 | Plinth beam - 1186.78Rmt |  |  |  | 0 |  |  | 0%
2.7.1 | Supply of Reinforcement | Rmt |  |  | 0 |  |  | 0%
2.7.2 | Shuttering | Rmt |  |  | 0 |  |  | 0%
2.7.3 | Concrete | Rmt |  |  | 0 |  |  | 0%

## WCP- SS (hidden)
URC Construction (P) Ltd
Odisha Bridge & Construction Corporation Limited
Development of Maa Samaleswari Temple Area
Name of The Building : Shoe Store |  |  | Work Completed Percentage Details
Sl. no | Description of Items | Unit | Completed Items |  |  | % For Completed Items |  |  | Remarks
|  |  | Upto Previous Bill | Current Bill | Cumulative Bill | Upto Previous Bill | Current Bill | Cumulative Bill
2 | CONSTRUCTION STAGE
A | On Completion up to Plinth
2.1 | Excavation | Ls |  | 1 | 1 |  | 100% | 100%
2.2 | ATT | Ls |  |  | 0 |  | 0% | 0%
2.3 | PCC | Ls |  |  | 0 |  | 0% | 0%
2.4 | Footings - 42 nos |  |  |  | 0 |  |  | 0%
2.4.1 | Supply of Reinforcement | Nos |  | 42 | 42 |  | 100% | 100%
2.4.2 | Shuttering | Nos |  |  | 0 |  | 0% | 0%
2.4.3 | Concrete | Nos |  |  | 0 |  | 0% | 0%
2.5 | Column - 42 nos |  |  |  | 0 |  |  | 0%
2.5.1 | Supply of Reinforcement | Nos |  | 42 | 42 |  | 100% | 100%
2.5.2 | Shuttering | Nos |  |  | 0 |  | 0% | 0%
2.5.3 | Concrete | Nos |  |  | 0 |  | 0% | 0%
2.6 | Backfilling | Ls |  |  | 0 |  |  | 0%
2.7 | Plinth beam - 127.40Rmt |  |  |  | 0 |  |  | 0%
2.7.1 | Supply of Reinforcement | Rmt |  |  | 0 |  |  | 0%
2.7.2 | Shuttering | Rmt |  |  | 0 |  |  | 0%
2.7.3 | Concrete | Rmt |  |  | 0 |  |  | 0%

## Supply of Steel (hidden)
URC Construction (P) Ltd
Odisha Bridge & Construction Corporation Limited
Development of Maa Samaleswari Temple
Supply of Steel Reinforcement Statement upto RAB 01
Sl no | Date | Supplier | Brand/ Grade | Invoice no | Dia wise Quantity |  |  |  |  | Total Quantity | Bill Amount | MTC No | Remarks
[5 empty] | 8mm | 10mm | 12 mm | 16mm | 20mm
1 | 2022-06-16 | Shyam Steel Industries Limited | SHYAM/ FE500D | 2310102845 |  | 11.9 |  | 8 | 19.91 | 39.81 | 2207443 | A/1001/22/0015394, 95, 96
2 | 2022-06-22 | Shyam Steel Industries Limited | SHYAM/ FE500D | 2310103113 |  |  |  | 31.99 |  | 31.99 | 1769047 | A/1001/22/0015759
3 | 2022-06-24 | Shyam Steel Industries Limited | SHYAM/ FE500D | 2310103203 |  |  | 29.91 |  |  | 29.91 | 1654023 | C/1001/22/0012365
4 | 2022-07-13 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000019163 |  |  | 33.58 |  |  | 33.58 | 1880480 | 0000453481
5 | 2022-07-15 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000019570 |  |  |  | 31.94 |  | 31.94 | 1788640 | 0000454155
6 | 2022-07-15 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000019571 |  | 12.119 |  | 19.181 |  | 31.3 | 1761889.25 | 0000454153, 0000454154
7 | 2022-07-16 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000019831 |  |  | 3.023 | 22.275 | 6.342 | 31.64 | 1771840 | 0000454570, 0000454571, 0000454572
8 | 2022-07-16 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000019804 | 21.59 |  |  | 9.87 |  | 31.46 | 1804940 | 0000454554, 0000454555
9 | 2022-07-18 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000020375 |  |  |  |  | 31.54 | 31.54 | 1766240 | 0000455418
10 | 2022-08-14 | Jindal Steel & Power Limited | JINDAL/ FE550D | RV6000027619 |  | 3.212 | 3.02 | 6.445 | 18.823 | 31.5 | 1744359.04 | 0000463093, 0000463094, 0000463106, 0000463107
| Total |  |  |  | 21.59 | 27.231 | 69.533 | 129.701 | 76.615 | 324.67 | 18148901.29
Note : Invoice and Bill Enclosed For This Statement.

## Abs-Royalty (hidden)
URC Construction (P) Ltd
Odisha Bridge & Construction Corporation Limited
Development of Maa Samaleswari Temple Area
Abstract For Royalty Amount | [14 empty] | RAB 01
Sl. no | Description of work | Unit | Concrete Quantity |  |  | Co-Efficient |  | Fine- aggreagate Amount |  |  |  | Coarse- aggreagate Amount |  |  |  | Remarks
|  |  | Upto Previous Bill, (A) | Current Bill, (B) | Cumulative Bill, (A+B) | Fine- aggreagate, (C) | Coarse- aggreagate, (D) | Rate, (E) | Upto Previous Bill, {F = (A xC xE )} | Current Bill, {G = (B xC xE )} | Cumulative Bill, (F+G) | Rate, (H) | Upto Previous Bill, {J = (A xD xH )} | Current Bill, {K = (B xD xH )} | Cumulative Bill, (J+K)
1 | MIX 10 grade | Cum |  | 51.5 | 51.5 | 0.46 | 0.9 | 35 | 0 | 829.15 | 829.15 | 130 | 0 | 6025.5 | 6025.5
2 | MIX 15 grade | Cum |  | 0 | 0 | 0.54 | 0.67 | 35 | 0 | 0 | 0 | 130 | 0 | 0 | 0
3 | MIX 20 grade | Cum |  | 0 |  | 0.47 | 0.74 | 35 | 0 | 0 | 0 | 130 | 0 | 0 | 0
4 | MIX 25 grade | Cum |  | 169.5 | 169.5 | 0.48 | 0.69 | 35 | 0 | 2847.6 | 2847.6 | 130 | 0 | 15204.15 | 15204.15
5 | MIX 30 grade | Cum |  | 0 | 0 | 0.46 | 0.68 | 35 | 0 | 0 | 0 | 130 | 0 | 0 | 0
Total |  |  | 0 | 221 | 221 |  |  |  | 0 | 3676.75 | 3676.75 |  | 0 | 21229.65 | 21229.65

## Concrete Pour Details (hidden)
URC Construction (P) Ltd
Odisha Bridge & Construction Corporation Limited
Development of Maa Samaleswari Temple Area
Concrete Pouring Details For Royalty | [7 empty] | RAB 01
Sl. no | Date | Building | Name of the Structure | Grade of Concrete Quantity in Cum |  |  |  |  | Remarks
|  |  |  | M10 | M15 | M20 | M25 | M30
1 | 2022-07-28 | Vending Zone | Footing PCC | 5.5
2 | 2022-07-29 | Vending Zone | Footing PCC | 5.5
3 | 2022-07-30 | Vending Zone | Footing PCC | 3
4 | 2022-08-01 | Vending Zone | Footing PCC | 5
5 | 2022-08-02 | Vending Zone | Footing PCC | 3.5
6 | 2022-08-06 | Vending Zone | Footing PCC | 3.5
7 | 2022-08-08 | Vending Zone | Footing PCC | 9
8 | 2022-08-16 | Vending Zone | Footing RCC |  |  |  | 8.5
9 | 2022-08-17 | Vending Zone | Footing RCC |  |  |  | 25
10 | 2022-08-18 | Vending Zone | Footing RCC |  |  |  | 31
11 | 2022-08-19 | Vending Zone | Footing RCC |  |  |  | 30
12 | 2022-08-22 | Vending Zone | Column RCC |  |  |  | 3.5
13 | 2022-08-23 | Vending Zone | Footing RCC |  |  |  | 23.5
|  |  | Column RCC |  |  |  | 3
14 | 2022-08-24 | Vending Zone | Column RCC |  |  |  | 3.5
15 | 2022-08-25 | Vending Zone | Footing RCC |  |  |  | 15.5
|  |  | Column RCC |  |  |  | 2.5
16 | 2022-08-26 | Vending Zone | Footing RCC |  |  |  | 6.5
|  |  | Column RCC |  |  |  | 2.5
17 | 2022-08-27 | Vending Zone | Column RCC |  |  |  | 1.5
18 | 2022-08-29 | Vending Zone | Footing PCC | 5
|  |  | Column RCC |  |  |  | 2.5
19 | 2022-08-30 | Vending Zone | Footing PCC | 2
20 | 2022-08-31 | Vending Zone | Footing PCC | 9.5
|  |  | Footing RCC |  |  |  | 10.5
| Total |  |  | 51.5 | 0 |  | 169.5 | 0